## Sheet1
Historic Centre of Vienna - Progress and Actions (to be) taken towards a DSOC 2018 / 2019
Objective | # | Action | Decision | Lead partner(s) | Progress / Actions (to be) taken | National Priority & Timeline | Comments
A. Effective and adequate planning controls for height, volume and building density respecting the OUV | 1 | Need for new tools to guide the development process towards sustainable development that protects the attributes of the OUV, and the specific recommendations of the 2015 mission to the property. | 42 COM 7A 18 / § 3 | State Party / City of Vienna | Development of a Management Plan by the City of Vienna (in cooperation i.a. with Universities, Experts, ICOMOS Austria, national and international Organisations, Administration Units and Representatives of Civils Society) | Preparatory Operations started in January 2019; concrete actions shall be carried out by a modular system: first half of 2020 resarch, discussions, debates; second half of 2020 collection of reactions, drafting. 2021: Final draft and editing. | The complete action will take about two years. The final result shall be submitted to the World Heritage Centre and ICOMOS International and adopted by the Municipal Council of Vienna.
| 2 | Process put in place by the State Party together with the City of Vienna in order to establish a clear milestone plan addressing the Commitee's decisions / Three Stage Process to address the substantive threats posed by current planning instruments and new developments that led to danger lisiting | 42 COM 7A 18 / § 4 and 8 | State Party | Independent Expert Workshop / Heritage Impact Assessment concerning the Heumarkt Neu Project against the backdrop of the general development of the property since 2001 / Advisory Mission to the Historic Centre of Vienna | The process started in March 2018; the last stage was completed mid November 2018. The results of the HIA and the Mission Report were presented to the public on 18th March 2019 and submitted to the World Heritage Centre for publication on the Website. | The results constitute the bedrock for any further actions to be taken. Hence the Mission Report together with the HIA have to be seen as a major basis for the development of the above mentionded Management Plan.
| 3 | Halt any further approvals for high-rise projects and the implementation of already approved projects, pending the adoption of the Desired State of Conservation Report and corrective measures by the Committee | 42 COM 7A 18 / § 7 | State Party | No plans or applications for new high-rise projects are currently known that would affect the Historic Centre of Vienna. The implementation of the "Heumarkt Neu" at present is halted due to a legal procedure concerning a possible investigation of the environmental impacts of the project. | The HIA and the Mission Report 2019 recommended a 2 years moratorium for the Heumarkt Neu project with the objective to explore compatible alternatives for the current project. The Lord Mayor of the City of Vienna informed the Federal Chancellery that "during the next months manifold discussions with all stakeholders, i.a. with the developer, shall take place to find out, whether and which possibilites exist to develop the project in the interest of a better compatibility with the World Heritage." | Currently the legal situation of the project stands as follows: The adpotion of the new zoning plan by the Municipal Council of Vienna in 2017 provides for the legal planning of the current project. The developer applied for buidling permission end of November 2018; no building permission was issued nor is it possible to proceed with the approval procedure due to an legal investigation set off by the Austrian Federal Administrative Court examining the necessity of carrying out an environmental impact assessment. The latter and possible subsequent legal steps will halt the implementation of the project for (the next) years.
| 4 | Require that all present and future high-rise projects are evaluated through a comprehensive Heritage Impact Assessment (HIA), prepared in accordance with the 2011 ICOMOS Guidance on HIAs for Cultural World Heritage properties, including reference to 3D visual simulations, so that the effects of the proposed development on the OUV of the property can be properly considered | 41 COM 7B.42, § 7d | State Party | The required HIA concerning the project "Heumarkt Neu" against the backdrop of the general development of the property since 2001 was commissioned by the Federal Chancellery and based on a comprehensive Scoping Report that involved the authorities of the City of Vienna and the representatives of the developer. The elboration of the HIA also included consultations with representatives of the civil society. A HIA concerning the project on Karlsplatz (extension of the Wien Museum and Winterthur Building) is no longer necessary according to the results of the Mission Report 2019. | The HIA was commissioned in late spring 2018. The scoping report was elaborated from early summer to September 2018. Due to the huge amount of data, the elaboration of detailed 3D visualisations and the need for repeated consultations with all stakeholders, the elaboration took longer than initially scheduled. The results are public available since 18th March 2019 via the websites of the World Heritage Centre and the Federal Chancellery. | At present no further high-rise projects or large scale developments that could affect the Historic Centre of Vienna are known to the Federal Chancellery.
| 5 | Incorporate the intent of the resolution of the City Council of Vienna, dated 5 May 2017 within the revised planning rules and guidelines | 41 COM 7B§ 7. e | City of Vienna | This action will be part of the elaboration of the management plan. | The implementation is possible in 2021 at the earliest.
| 6 | Moratorium on all high-rise projects until the planning controls have been amended | 41 COM 7B § 9 and 42 COM 7A 18 § 7 | State Party | A two years moratorium for the Heumarkt Neu project is an important recommendation by the Mission Report 2019 and the HIA concerning the project. | The City of Vienna agreed to comply with the recommendation stated by the Mission Report and the HIA. | At present no further high-rise projects or large scale developments that could affect the Historic Centre of Vienna are known to the Federal Chancellery.
B. Design changes for the Vienna Ice Skating Club - Intercontinental Hotel - Vienna Konzerthaus with no adverse impact on the World Heritage property's OUV | 7 | Submit a further revised design to the World Heritage Centre, for review by the Advisory Bodies, which is consistent with the recommendations of the 2012 and 2015 mission and which will protect the attributes of OUV of the property | 41 COM 7B§ 6.; §10. | State Party City of Vienna Advisory Bodies | The redevelopment and the redesign of the project was recommended by the Mission Report 2019 in March 2019. | The HIA assessed the project in the design of December 2016. Possibilites to meet this recommendation shall be assessed during the next months as reported by the City of Vienna.
| 8 | Moratorium on all decisions regarding its implementation before the submission and review of the revised design | 41 COM 7B§ 6. | State Party | Please note item 3 and 7 | Please note item 3 and7 | Please note item 3 and 7
C. Design changes for the Karlsplatz area developments with no adverse impat on the World Heritage property's OUV | 9 | Ensure that the proposals are evaluated through a comprehensive HIA, prepared in accordance with the 2011 ICOMOS Guidance on HIAs for Cultural World Heritage properties | 41 COM 7B§ 8 and 42 COM 7A 18 § 6 | State Party | Comprehensive Information by the State Party and the City of Vienna was submitted to the World Heritage Centre in 2018. The project was assessed by the Advisory Mission; additional information was provided subsequently to the mission. | The Mission Report 2019 noted that the project had developed in a very positive way and that an HIA is no longer required.
| 10 | Ensure that comprehensive documentation, drawings and visualizations of the planned interventions as observed from ground level are submitted to the World Heritage Centre for review by the Advisory Bodies | 41 COM 7B§ 8. | State Party City of Vienna Advisory Bodies | Additional information concerning the final design of the entrance solution for the Wien Museum will be submitted as soon as available. Any construction details have to be carried out in accordance with the decree issued by the Federal Monuments Authority and after predefinition by the latter. | At present no definite date for the beginning of construction works was stipulated. | Any steps concerning the implementation of the building project will be done in close cooperation with and according to predefinitions by the Federal Monuments Authority.
D. Effective protection of historic roof constructions | 11 | Complete the study on historic roof constructions in the Historic Centre of Vienna | 41 COM 7B§ 5. | State Party Federal Monuments Authoritiy City of Vienna | The Study on historic roof constructions was completed and presented to the experts of the Advisory Mission in November 2018. | The findings of the study shall be incorporated in the elaboartion of the Management Plan. | The possibiliy to extend the study to include steel and composite construcitions currently is assessed in cooperation with the Federal Monuments Authority and the City of Vienna.
| 12 | Moratorium on projects that involve any modification of the roofscapes within the property until the study has been completed. | 41 COM 7B§ 5. | State Party / City of Vienna | Two projects for roof extensions / conversions of significant baroque gambrel roofs amplified the concerns expressed by the mission reports 2012 and 2015: Schwertgasse 3 and Bauernmarkt 1 (information on these projects were submitted to the World Heritage Centre and ICOMOS International between 2014 and 2016). Both projects were stopped respectively completely revised. | No permission was granted for a roof conversion in Schwertgasse 3. The project Bauernmarkt 1 was withdrawn and completely revised: the historic roof construction remains in place and there will be no contemporary design for the overall appearance of the roof. | A general way forward concerning roof conversions will be part of the elaboration of the management plan.
E. Effective protection of historic gardens | 13 | Information concerning the implementation of a beer garden project in the area of the so called "Belvedere Stöckl" (a former restaurant closed in 2006) was required by the World Heritage Centre and ICOMOS International. | not part of a decision | State Party / ICOMOS Austria / Representatives of the Owner | Information about the project was provided to the World Heritage Centre by the State Party and by ICOMOS Austria. The area and the project was assessed by the Advisory Mission in November 2018. The Mission Report 2019 noted the "degraded character" of the project area and recommends i.a. the elaboration of a long-term vision and an integrated spacial conservation plan for the gardens and the palace. | Therefore, the Federal Chancellery together with the Federal Monuments Authority and ICOMOS Austria will provide a comprehensive report on the actual impact of the current planning on the OUV of the property by the end of 2019. This report will also include an outline of the already existing preservation plan for the palace and the garden and the projected amendments with the objective to meet the recent challenges, i.a. climate change.