## Worksheet
CSR Subpart | Measure name | Milestone/target name | Target date for implementation (latest reporting) | Status (MS reporting) | REPowerEU
2019.CSR1.subpart1 | Enhancing primary health care | Platform on primary health care and related measures | 2022-12-31 | Completed | FALSE
2020.CSR1.subpart2 | Enhancing primary health care | Platform on primary health care and related measures | 2022-12-31 | Completed | FALSE
2023.CSR1.subpart6 | Enhancing primary health care | Platform on primary health care and related measures | 2022-12-31 | Completed | FALSE
2024.CSR1.subpart3 | Enhancing primary health care | Platform on primary health care and related measures | 2022-12-31 | Completed | FALSE
2019.CSR1.subpart1 | Enhancing primary health care | Promotional events in the context of the platform/incubator programme | 2023-12-31 | Completed | FALSE
2020.CSR1.subpart2 | Enhancing primary health care | Promotional events in the context of the platform/incubator programme | 2023-12-31 | Completed | FALSE
2023.CSR1.subpart6 | Enhancing primary health care | Promotional events in the context of the platform/incubator programme | 2023-12-31 | Completed | FALSE
2024.CSR1.subpart3 | Enhancing primary health care | Promotional events in the context of the platform/incubator programme | 2023-12-31 | Completed | FALSE
2019.CSR1.subpart1 | Funding of primary health care projects | Adoption and publication of funding guidelines for primary health care projects | 2021-12-30 | Fulfilled | FALSE
2020.CSR1.subpart2 | Funding of primary health care projects | Adoption and publication of funding guidelines for primary health care projects | 2021-12-30 | Fulfilled | FALSE
2023.CSR1.subpart6 | Funding of primary health care projects | Adoption and publication of funding guidelines for primary health care projects | 2021-12-30 | Fulfilled | FALSE
2024.CSR1.subpart3 | Funding of primary health care projects | Adoption and publication of funding guidelines for primary health care projects | 2021-12-30 | Fulfilled | FALSE
2019.CSR1.subpart1 | Funding of primary health care projects | Funding of primary health care projects | 2023-12-31 | Completed | FALSE
2020.CSR1.subpart2 | Funding of primary health care projects | Funding of primary health care projects | 2023-12-31 | Completed | FALSE
2023.CSR1.subpart6 | Funding of primary health care projects | Funding of primary health care projects | 2023-12-31 | Completed | FALSE
2024.CSR1.subpart3 | Funding of primary health care projects | Funding of primary health care projects | 2023-12-31 | Completed | FALSE
2019.CSR1.subpart1 | Funding of primary health care projects | Funding of primary health care projects | 2025-06-30 | Completed | FALSE
2020.CSR1.subpart2 | Funding of primary health care projects | Funding of primary health care projects | 2025-06-30 | Completed | FALSE
2023.CSR1.subpart6 | Funding of primary health care projects | Funding of primary health care projects | 2025-06-30 | Completed | FALSE
2024.CSR1.subpart3 | Funding of primary health care projects | Funding of primary health care projects | 2025-06-30 | Completed | FALSE
2019.CSR1.subpart1 | Development of the electronic mother child pass platform including the interfaces to the early aid networks | Entry into force of the law defining the framework for the electronic ‘mother-child pass’ | 2023-06-30 | Completed | FALSE
2020.CSR1.subpart2 | Development of the electronic mother child pass platform including the interfaces to the early aid networks | Entry into force of the law defining the framework for the electronic ‘mother-child pass’ | 2023-06-30 | Completed | FALSE
2019.CSR1.subpart1 | Development of the electronic mother child pass platform including the interfaces to the early aid networks | Award of the electronic 'mother child pass' platform programming contract | 2023-12-31 | Completed | FALSE
2020.CSR1.subpart2 | Development of the electronic mother child pass platform including the interfaces to the early aid networks | Award of the electronic 'mother child pass' platform programming contract | 2023-12-31 | Completed | FALSE
2019.CSR1.subpart1 | National roll-out of ‘early aid’ for socially disadvantaged pregnant women, their young children and families | Identification and entrustment of the implementation bodies | 2022-12-31 | Completed | FALSE
2020.CSR1.subpart2 | National roll-out of ‘early aid’ for socially disadvantaged pregnant women, their young children and families | Identification and entrustment of the implementation bodies | 2022-12-31 | Completed | FALSE
2019.CSR1.subpart1 | National roll-out of ‘early aid’ for socially disadvantaged pregnant women, their young children and families | National roll-out of ‘early aid’ | 2023-09-30 | Completed | FALSE
2020.CSR1.subpart2 | National roll-out of ‘early aid’ for socially disadvantaged pregnant women, their young children and families | National roll-out of ‘early aid’ | 2023-09-30 | Completed | FALSE
2019.CSR1.subpart1 | National roll-out of ‘early aid’ for socially disadvantaged pregnant women, their young children and families | National roll-out of ‘early aid’ | 2024-09-30 | Completed | FALSE
2020.CSR1.subpart2 | National roll-out of ‘early aid’ for socially disadvantaged pregnant women, their young children and families | National roll-out of ‘early aid’ | 2024-09-30 | Completed | FALSE
2019.CSR1.subpart1 | Investment in the implementation of community nurses | Start of community nurses work | 2021-09-29 | Fulfilled | FALSE
2020.CSR1.subpart2 | Investment in the implementation of community nurses | Start of community nurses work | 2021-09-29 | Fulfilled | FALSE
2022.CSR1.subpart4 | Investment in the implementation of community nurses | Start of community nurses work | 2021-09-29 | Fulfilled | FALSE
2023.CSR1.subpart5 | Investment in the implementation of community nurses | Start of community nurses work | 2021-09-29 | Fulfilled | FALSE
2024.CSR1.subpart4 | Investment in the implementation of community nurses | Start of community nurses work | 2021-09-29 | Fulfilled | FALSE
2019.CSR1.subpart1 | Investment in the implementation of community nurses | Interim evaluation | 2022-12-31 | Completed | FALSE
2020.CSR1.subpart2 | Investment in the implementation of community nurses | Interim evaluation | 2022-12-31 | Completed | FALSE
2022.CSR1.subpart4 | Investment in the implementation of community nurses | Interim evaluation | 2022-12-31 | Completed | FALSE
2023.CSR1.subpart5 | Investment in the implementation of community nurses | Interim evaluation | 2022-12-31 | Completed | FALSE
2024.CSR1.subpart4 | Investment in the implementation of community nurses | Interim evaluation | 2022-12-31 | Completed | FALSE
2019.CSR1.subpart1 | Investment in the implementation of community nurses | 150 community nurses active at national level | 2024-12-31 | On track | FALSE
2020.CSR1.subpart2 | Investment in the implementation of community nurses | 150 community nurses active at national level | 2024-12-31 | On track | FALSE
2022.CSR1.subpart4 | Investment in the implementation of community nurses | 150 community nurses active at national level | 2024-12-31 | On track | FALSE
2023.CSR1.subpart5 | Investment in the implementation of community nurses | 150 community nurses active at national level | 2024-12-31 | On track | FALSE
2024.CSR1.subpart4 | Investment in the implementation of community nurses | 150 community nurses active at national level | 2024-12-31 | On track | FALSE
2019.CSR1.subpart2 | Reform to further develop care provision | Pilot projects on community nurses as element of the Reform of care provision, | 2021-09-26 | Fulfilled | FALSE
2020.CSR1.subpart2 | Reform to further develop care provision | Pilot projects on community nurses as element of the Reform of care provision, | 2021-09-26 | Fulfilled | FALSE
2022.CSR1.subpart4 | Reform to further develop care provision | Pilot projects on community nurses as element of the Reform of care provision, | 2021-09-26 | Fulfilled | FALSE
2023.CSR1.subpart5 | Reform to further develop care provision | Pilot projects on community nurses as element of the Reform of care provision, | 2021-09-26 | Fulfilled | FALSE
2024.CSR1.subpart4 | Reform to further develop care provision | Pilot projects on community nurses as element of the Reform of care provision, | 2021-09-26 | Fulfilled | FALSE
2019.CSR1.subpart2 | Reform to further develop care provision | Principles for the implementa-tion of long-term care target based governance (Ziel-steuerung Pflege) are established | 2022-12-31 | Completed | FALSE
2020.CSR1.subpart2 | Reform to further develop care provision | Principles for the implementa-tion of long-term care target based governance (Ziel-steuerung Pflege) are established | 2022-12-31 | Completed | FALSE
2022.CSR1.subpart4 | Reform to further develop care provision | Principles for the implementa-tion of long-term care target based governance (Ziel-steuerung Pflege) are established | 2022-12-31 | Completed | FALSE
2023.CSR1.subpart5 | Reform to further develop care provision | Principles for the implementa-tion of long-term care target based governance (Ziel-steuerung Pflege) are established | 2022-12-31 | Completed | FALSE
2024.CSR1.subpart4 | Reform to further develop care provision | Principles for the implementa-tion of long-term care target based governance (Ziel-steuerung Pflege) are established | 2022-12-31 | Completed | FALSE
2019.CSR1.subpart2 | Reform to further develop care provision | Start implementing the core elements of the reform of long-term care provision | 2024-03-31 | Completed | FALSE
2020.CSR1.subpart2 | Reform to further develop care provision | Start implementing the core elements of the reform of long-term care provision | 2024-03-31 | Completed | FALSE
2022.CSR1.subpart4 | Reform to further develop care provision | Start implementing the core elements of the reform of long-term care provision | 2024-03-31 | Completed | FALSE
2023.CSR1.subpart5 | Reform to further develop care provision | Start implementing the core elements of the reform of long-term care provision | 2024-03-31 | Completed | FALSE
2024.CSR1.subpart4 | Reform to further develop care provision | Start implementing the core elements of the reform of long-term care provision | 2024-03-31 | Completed | FALSE
2019.CSR1.subpart3 | Increase in effective retirement age | Establishment of the legal basis for the abolishment of the early retirement pension without deduction, as well as for the introduction of the early starter bonus and the postponement of the first pension increase (Aliquotierung) | 2020-12-30 | Fulfilled | FALSE
2019.CSR1.subpart3 | Increase in effective retirement age | Effective implementation of the early starter bonus (replacing early retirement pensions without deduction) and of the postponement of the first pension increase (Aliquotierung) | 2022-03-30 | Completed | FALSE
2019.CSR1.subpart3 | Pension splitting | Legislative proposal | 2024-08-31 | Completed | FALSE
2019.CSR1.subpart3 | Pension splitting | Entry into force of the law introducing automatic pension splitting | 2024-08-31 | Not completed | FALSE
2019.CSR1.subpart4 | Spending review focusing on green and digital transformation | Spending Review on the analysis of the climate and energy policy support and incentive landscape. | 2022-09-29 | Completed | FALSE
2022.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review on the analysis of the climate and energy policy support and incentive landscape. | 2022-09-29 | Completed | FALSE
2023.CSR1.subpart7 | Spending review focusing on green and digital transformation | Spending Review on the analysis of the climate and energy policy support and incentive landscape. | 2022-09-29 | Completed | FALSE
2024.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review on the analysis of the climate and energy policy support and incentive landscape. | 2022-09-29 | Completed | FALSE
2019.CSR1.subpart4 | Spending review focusing on green and digital transformation | Spending Review ‘Identifying synergies with the funding landscape of the Länder’ | 2023-09-30 | Completed | FALSE
2022.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Identifying synergies with the funding landscape of the Länder’ | 2023-09-30 | Completed | FALSE
2023.CSR1.subpart7 | Spending review focusing on green and digital transformation | Spending Review ‘Identifying synergies with the funding landscape of the Länder’ | 2023-09-30 | Completed | FALSE
2024.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Identifying synergies with the funding landscape of the Länder’ | 2023-09-30 | Completed | FALSE
2019.CSR1.subpart4 | Spending review focusing on green and digital transformation | Spending Review ‘Implementation of the EU taxonomy at national level’ | 2024-12-31 | On track | FALSE
2022.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Implementation of the EU taxonomy at national level’ | 2024-12-31 | On track | FALSE
2023.CSR1.subpart7 | Spending review focusing on green and digital transformation | Spending Review ‘Implementation of the EU taxonomy at national level’ | 2024-12-31 | On track | FALSE
2024.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Implementation of the EU taxonomy at national level’ | 2024-12-31 | On track | FALSE
2019.CSR1.subpart4 | Spending review focusing on green and digital transformation | Spending Review ‘Public-sector shareholding’ | 2025-06-30 | On track | FALSE
2022.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Public-sector shareholding’ | 2025-06-30 | On track | FALSE
2023.CSR1.subpart7 | Spending review focusing on green and digital transformation | Spending Review ‘Public-sector shareholding’ | 2025-06-30 | On track | FALSE
2024.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Public-sector shareholding’ | 2025-06-30 | On track | FALSE
2019.CSR1.subpart4 | Spending review focusing on green and digital transformation | Spending Review ‘Sustainability of Public Procurement’ | 2025-12-31 | Not completed | FALSE
2022.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Sustainability of Public Procurement’ | 2025-12-31 | Not completed | FALSE
2023.CSR1.subpart7 | Spending review focusing on green and digital transformation | Spending Review ‘Sustainability of Public Procurement’ | 2025-12-31 | Not completed | FALSE
2024.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Sustainability of Public Procurement’ | 2025-12-31 | Not completed | FALSE
2019.CSR1.subpart4 | Spending review focusing on green and digital transformation | Spending Review ‘Further advancement of digitalisation in public administration’ | 2023-09-30 | Completed | FALSE
2022.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Further advancement of digitalisation in public administration’ | 2023-09-30 | Completed | FALSE
2023.CSR1.subpart7 | Spending review focusing on green and digital transformation | Spending Review ‘Further advancement of digitalisation in public administration’ | 2023-09-30 | Completed | FALSE
2024.CSR1.subpart5 | Spending review focusing on green and digital transformation | Spending Review ‘Further advancement of digitalisation in public administration’ | 2023-09-30 | Completed | FALSE
2019.CSR2.subpart1 | Eco-social tax reform | Launch of the second stage of the work of the task force | 2021-06-29 | Fulfilled | FALSE
2020.CSR4.subpart1 | Eco-social tax reform | Launch of the second stage of the work of the task force | 2021-06-29 | Fulfilled | FALSE
2022.CSR1.subpart6 | Eco-social tax reform | Launch of the second stage of the work of the task force | 2021-06-29 | Fulfilled | FALSE
2022.CSR4.subpart1 | Eco-social tax reform | Launch of the second stage of the work of the task force | 2021-06-29 | Fulfilled | FALSE
2023.CSR1.subpart8 | Eco-social tax reform | Launch of the second stage of the work of the task force | 2021-06-29 | Fulfilled | FALSE
2023.CSR4.subpart1 | Eco-social tax reform | Launch of the second stage of the work of the task force | 2021-06-29 | Fulfilled | FALSE
2024.CSR1.subpart6 | Eco-social tax reform | Launch of the second stage of the work of the task force | 2021-06-29 | Fulfilled | FALSE
2024.CSR1.subpart7 | Eco-social tax reform | Launch of the second stage of the work of the task force | 2021-06-29 | Fulfilled | FALSE
2019.CSR2.subpart1 | Eco-social tax reform | Entry into force of the eco-social tax reform | 2022-03-30 | Completed | FALSE
2020.CSR4.subpart1 | Eco-social tax reform | Entry into force of the eco-social tax reform | 2022-03-30 | Completed | FALSE
2022.CSR1.subpart6 | Eco-social tax reform | Entry into force of the eco-social tax reform | 2022-03-30 | Completed | FALSE
2022.CSR4.subpart1 | Eco-social tax reform | Entry into force of the eco-social tax reform | 2022-03-30 | Completed | FALSE
2023.CSR1.subpart8 | Eco-social tax reform | Entry into force of the eco-social tax reform | 2022-03-30 | Completed | FALSE
2023.CSR4.subpart1 | Eco-social tax reform | Entry into force of the eco-social tax reform | 2022-03-30 | Completed | FALSE
2024.CSR1.subpart6 | Eco-social tax reform | Entry into force of the eco-social tax reform | 2022-03-30 | Completed | FALSE
2024.CSR1.subpart7 | Eco-social tax reform | Entry into force of the eco-social tax reform | 2022-03-30 | Completed | FALSE
2019.CSR2.subpart2 | Expansion of elementary education | Increasing rates of childcare for children under three years of age | 2025-09-30 | Completed | FALSE
2020.CSR2.subpart1 | Expansion of elementary education | Increasing rates of childcare for children under three years of age | 2025-09-30 | Completed | FALSE
2022.CSR3.subpart1 | Expansion of elementary education | Increasing rates of childcare for children under three years of age | 2025-09-30 | Completed | FALSE
2023.CSR3.subpart1 | Expansion of elementary education | Increasing rates of childcare for children under three years of age | 2025-09-30 | Completed | FALSE
2024.CSR3.subpart1 | Expansion of elementary education | Increasing rates of childcare for children under three years of age | 2025-09-30 | Completed | FALSE
2024.CSR3.subpart2 | Expansion of elementary education | Increasing rates of childcare for children under three years of age | 2025-09-30 | Completed | FALSE
2019.CSR2.subpart2 | Expansion of elementary education | Increasing rates of early childhood education for children aged three to six compatible with full-time employment of parents | 2025-09-30 | Completed | FALSE
2020.CSR2.subpart1 | Expansion of elementary education | Increasing rates of early childhood education for children aged three to six compatible with full-time employment of parents | 2025-09-30 | Completed | FALSE
2022.CSR3.subpart1 | Expansion of elementary education | Increasing rates of early childhood education for children aged three to six compatible with full-time employment of parents | 2025-09-30 | Completed | FALSE
2023.CSR3.subpart1 | Expansion of elementary education | Increasing rates of early childhood education for children aged three to six compatible with full-time employment of parents | 2025-09-30 | Completed | FALSE
2024.CSR3.subpart1 | Expansion of elementary education | Increasing rates of early childhood education for children aged three to six compatible with full-time employment of parents | 2025-09-30 | Completed | FALSE
2024.CSR3.subpart2 | Expansion of elementary education | Increasing rates of early childhood education for children aged three to six compatible with full-time employment of parents | 2025-09-30 | Completed | FALSE
2019.CSR2.subpart3 | Labour market: one-stop shop | Conceptual development | 2021-09-28 | Fulfilled | FALSE
2022.CSR3.subpart2 | Labour market: one-stop shop | Conceptual development | 2021-09-28 | Fulfilled | FALSE
2023.CSR3.subpart2 | Labour market: one-stop shop | Conceptual development | 2021-09-28 | Fulfilled | FALSE
2024.CSR3.subpart2 | Labour market: one-stop shop | Conceptual development | 2021-09-28 | Fulfilled | FALSE
2019.CSR2.subpart3 | Labour market: one-stop shop | Start of operations | 2022-03-30 | Completed | FALSE
2022.CSR3.subpart2 | Labour market: one-stop shop | Start of operations | 2022-03-30 | Completed | FALSE
2023.CSR3.subpart2 | Labour market: one-stop shop | Start of operations | 2022-03-30 | Completed | FALSE
2024.CSR3.subpart2 | Labour market: one-stop shop | Start of operations | 2022-03-30 | Completed | FALSE
2019.CSR2.subpart3 | Education bonus | Entry into force of the Unemployment Insurance Act and the publication of the Funding Guidelines on the Ministries’ website | 2020-12-30 | Fulfilled | FALSE
2020.CSR2.subpart2 | Education bonus | Entry into force of the Unemployment Insurance Act and the publication of the Funding Guidelines on the Ministries’ website | 2020-12-30 | Fulfilled | FALSE
2022.CSR3.subpart2 | Education bonus | Entry into force of the Unemployment Insurance Act and the publication of the Funding Guidelines on the Ministries’ website | 2020-12-30 | Fulfilled | FALSE
2023.CSR3.subpart2 | Education bonus | Entry into force of the Unemployment Insurance Act and the publication of the Funding Guidelines on the Ministries’ website | 2020-12-30 | Fulfilled | FALSE
2024.CSR3.subpart2 | Education bonus | Entry into force of the Unemployment Insurance Act and the publication of the Funding Guidelines on the Ministries’ website | 2020-12-30 | Fulfilled | FALSE
2019.CSR2.subpart3 | Education bonus | Education bonuses disbursed | 2021-12-30 | Fulfilled | FALSE
2020.CSR2.subpart2 | Education bonus | Education bonuses disbursed | 2021-12-30 | Fulfilled | FALSE
2022.CSR3.subpart2 | Education bonus | Education bonuses disbursed | 2021-12-30 | Fulfilled | FALSE
2023.CSR3.subpart2 | Education bonus | Education bonuses disbursed | 2021-12-30 | Fulfilled | FALSE
2024.CSR3.subpart2 | Education bonus | Education bonuses disbursed | 2021-12-30 | Fulfilled | FALSE
2019.CSR2.subpart3 | Education bonus | Education bonus measure evaluated | 2022-03-30 | Completed | FALSE
2020.CSR2.subpart2 | Education bonus | Education bonus measure evaluated | 2022-03-30 | Completed | FALSE
2022.CSR3.subpart2 | Education bonus | Education bonus measure evaluated | 2022-03-30 | Completed | FALSE
2023.CSR3.subpart2 | Education bonus | Education bonus measure evaluated | 2022-03-30 | Completed | FALSE
2024.CSR3.subpart2 | Education bonus | Education bonus measure evaluated | 2022-03-30 | Completed | FALSE
2019.CSR2.subpart3 | Promoting re-skilling and up-skilling | Ensuring the preconditions for re- and upskilling | 2020-12-30 | Fulfilled | FALSE
2020.CSR2.subpart2 | Promoting re-skilling and up-skilling | Ensuring the preconditions for re- and upskilling | 2020-12-30 | Fulfilled | FALSE
2022.CSR3.subpart2 | Promoting re-skilling and up-skilling | Ensuring the preconditions for re- and upskilling | 2020-12-30 | Fulfilled | FALSE
2023.CSR3.subpart1 | Promoting re-skilling and up-skilling | Ensuring the preconditions for re- and upskilling | 2020-12-30 | Fulfilled | FALSE
2023.CSR3.subpart2 | Promoting re-skilling and up-skilling | Ensuring the preconditions for re- and upskilling | 2020-12-30 | Fulfilled | FALSE
2024.CSR3.subpart1 | Promoting re-skilling and up-skilling | Ensuring the preconditions for re- and upskilling | 2020-12-30 | Fulfilled | FALSE
2024.CSR3.subpart2 | Promoting re-skilling and up-skilling | Ensuring the preconditions for re- and upskilling | 2020-12-30 | Fulfilled | FALSE
2019.CSR2.subpart3 | Promoting re-skilling and up-skilling | First annual overview | 2022-03-30 | Completed | FALSE
2020.CSR2.subpart2 | Promoting re-skilling and up-skilling | First annual overview | 2022-03-30 | Completed | FALSE
2022.CSR3.subpart2 | Promoting re-skilling and up-skilling | First annual overview | 2022-03-30 | Completed | FALSE
2023.CSR3.subpart1 | Promoting re-skilling and up-skilling | First annual overview | 2022-03-30 | Completed | FALSE
2023.CSR3.subpart2 | Promoting re-skilling and up-skilling | First annual overview | 2022-03-30 | Completed | FALSE
2024.CSR3.subpart1 | Promoting re-skilling and up-skilling | First annual overview | 2022-03-30 | Completed | FALSE
2024.CSR3.subpart2 | Promoting re-skilling and up-skilling | First annual overview | 2022-03-30 | Completed | FALSE
2019.CSR2.subpart3 | Promoting re-skilling and up-skilling | People benefitting from re-skilling and up-skilling. | 2022-12-31 | Completed | FALSE
2020.CSR2.subpart2 | Promoting re-skilling and up-skilling | People benefitting from re-skilling and up-skilling. | 2022-12-31 | Completed | FALSE
2022.CSR3.subpart2 | Promoting re-skilling and up-skilling | People benefitting from re-skilling and up-skilling. | 2022-12-31 | Completed | FALSE
2023.CSR3.subpart1 | Promoting re-skilling and up-skilling | People benefitting from re-skilling and up-skilling. | 2022-12-31 | Completed | FALSE
2023.CSR3.subpart2 | Promoting re-skilling and up-skilling | People benefitting from re-skilling and up-skilling. | 2022-12-31 | Completed | FALSE
2024.CSR3.subpart1 | Promoting re-skilling and up-skilling | People benefitting from re-skilling and up-skilling. | 2022-12-31 | Completed | FALSE
2024.CSR3.subpart2 | Promoting re-skilling and up-skilling | People benefitting from re-skilling and up-skilling. | 2022-12-31 | Completed | FALSE
2019.CSR2.subpart4 | Improved access to education | Entry into force of the amended School Education Act | 2023-09-01 | Completed | FALSE
2020.CSR2.subpart1 | Improved access to education | Entry into force of the amended School Education Act | 2023-09-01 | Completed | FALSE
2022.CSR3.subpart2 | Improved access to education | Entry into force of the amended School Education Act | 2023-09-01 | Completed | FALSE
2023.CSR3.subpart2 | Improved access to education | Entry into force of the amended School Education Act | 2023-09-01 | Completed | FALSE
2024.CSR3.subpart2 | Improved access to education | Entry into force of the amended School Education Act | 2023-09-01 | Completed | FALSE
2019.CSR2.subpart4 | Improved access to education | Entry into force of the legislation on the implementation of additional modules of the national standardised assessments | 2024-06-30 | Completed | FALSE
2020.CSR2.subpart1 | Improved access to education | Entry into force of the legislation on the implementation of additional modules of the national standardised assessments | 2024-06-30 | Completed | FALSE
2022.CSR3.subpart2 | Improved access to education | Entry into force of the legislation on the implementation of additional modules of the national standardised assessments | 2024-06-30 | Completed | FALSE
2023.CSR3.subpart2 | Improved access to education | Entry into force of the legislation on the implementation of additional modules of the national standardised assessments | 2024-06-30 | Completed | FALSE
2024.CSR3.subpart2 | Improved access to education | Entry into force of the legislation on the implementation of additional modules of the national standardised assessments | 2024-06-30 | Completed | FALSE
2019.CSR2.subpart4 | Improved access to education | Entry into force of the legislation on establishing criteria for the specification of the socio-economic baseline of schools | 2025-12-31 | Not completed | FALSE
2020.CSR2.subpart1 | Improved access to education | Entry into force of the legislation on establishing criteria for the specification of the socio-economic baseline of schools | 2025-12-31 | Not completed | FALSE
2022.CSR3.subpart2 | Improved access to education | Entry into force of the legislation on establishing criteria for the specification of the socio-economic baseline of schools | 2025-12-31 | Not completed | FALSE
2023.CSR3.subpart2 | Improved access to education | Entry into force of the legislation on establishing criteria for the specification of the socio-economic baseline of schools | 2025-12-31 | Not completed | FALSE
2024.CSR3.subpart2 | Improved access to education | Entry into force of the legislation on establishing criteria for the specification of the socio-economic baseline of schools | 2025-12-31 | Not completed | FALSE
2019.CSR2.subpart4 | Remedial education package | Finalisation of the remedial education package and start with the measures in the schools | 2021-06-28 | Fulfilled | FALSE
2020.CSR2.subpart1 | Remedial education package | Finalisation of the remedial education package and start with the measures in the schools | 2021-06-28 | Fulfilled | FALSE
2024.CSR3.subpart2 | Remedial education package | Finalisation of the remedial education package and start with the measures in the schools | 2021-06-28 | Fulfilled | FALSE
2019.CSR2.subpart4 | Remedial education package | Support measures during the school year are completed. Provision of supplementary classes including during the holidays | 2021-12-30 | Fulfilled | FALSE
2020.CSR2.subpart1 | Remedial education package | Support measures during the school year are completed. Provision of supplementary classes including during the holidays | 2021-12-30 | Fulfilled | FALSE
2024.CSR3.subpart2 | Remedial education package | Support measures during the school year are completed. Provision of supplementary classes including during the holidays | 2021-12-30 | Fulfilled | FALSE
2019.CSR2.subpart4 | Remedial education package | Evaluation of the additional teaching staff deployment | 2022-03-30 | Completed | FALSE
2020.CSR2.subpart1 | Remedial education package | Evaluation of the additional teaching staff deployment | 2022-03-30 | Completed | FALSE
2024.CSR3.subpart2 | Remedial education package | Evaluation of the additional teaching staff deployment | 2022-03-30 | Completed | FALSE
2019.CSR3.subpart1 | IPCEI Microelectronics and Connectivity | Climate-related eligibility criteria established in call documents | 2021-12-31 | Fulfilled | FALSE
2020.CSR3.subpart5 | IPCEI Microelectronics and Connectivity | Climate-related eligibility criteria established in call documents | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart2 | IPCEI Microelectronics and Connectivity | Climate-related eligibility criteria established in call documents | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart3 | IPCEI Microelectronics and Connectivity | Climate-related eligibility criteria established in call documents | 2021-12-31 | Fulfilled | FALSE
2019.CSR3.subpart1 | IPCEI Microelectronics and Connectivity | National selection of projects to support the development of innovative microelectronics and connectivity technologies | 2021-12-31 | Fulfilled | FALSE
2020.CSR3.subpart5 | IPCEI Microelectronics and Connectivity | National selection of projects to support the development of innovative microelectronics and connectivity technologies | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart2 | IPCEI Microelectronics and Connectivity | National selection of projects to support the development of innovative microelectronics and connectivity technologies | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart3 | IPCEI Microelectronics and Connectivity | National selection of projects to support the development of innovative microelectronics and connectivity technologies | 2021-12-31 | Fulfilled | FALSE
2019.CSR3.subpart1 | IPCEI Microelectronics and Connectivity | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2020.CSR3.subpart5 | IPCEI Microelectronics and Connectivity | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2022.CSR4.subpart2 | IPCEI Microelectronics and Connectivity | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart3 | IPCEI Microelectronics and Connectivity | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2019.CSR3.subpart1 | IPCEI Hydrogen | National selection of projects to support the development of hydrogen production, storage and applications | 2021-09-30 | Fulfilled | FALSE
2020.CSR3.subpart5 | IPCEI Hydrogen | National selection of projects to support the development of hydrogen production, storage and applications | 2021-09-30 | Fulfilled | FALSE
2022.CSR4.subpart1 | IPCEI Hydrogen | National selection of projects to support the development of hydrogen production, storage and applications | 2021-09-30 | Fulfilled | FALSE
2022.CSR4.subpart2 | IPCEI Hydrogen | National selection of projects to support the development of hydrogen production, storage and applications | 2021-09-30 | Fulfilled | FALSE
2023.CSR4.subpart1 | IPCEI Hydrogen | National selection of projects to support the development of hydrogen production, storage and applications | 2021-09-30 | Fulfilled | FALSE
2023.CSR4.subpart2 | IPCEI Hydrogen | National selection of projects to support the development of hydrogen production, storage and applications | 2021-09-30 | Fulfilled | FALSE
2023.CSR4.subpart3 | IPCEI Hydrogen | National selection of projects to support the development of hydrogen production, storage and applications | 2021-09-30 | Fulfilled | FALSE
2024.CSR4.subpart1 | IPCEI Hydrogen | National selection of projects to support the development of hydrogen production, storage and applications | 2021-09-30 | Fulfilled | FALSE
2019.CSR3.subpart1 | IPCEI Hydrogen | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2020.CSR3.subpart5 | IPCEI Hydrogen | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2022.CSR4.subpart1 | IPCEI Hydrogen | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2022.CSR4.subpart2 | IPCEI Hydrogen | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart1 | IPCEI Hydrogen | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart2 | IPCEI Hydrogen | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart3 | IPCEI Hydrogen | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2024.CSR4.subpart1 | IPCEI Hydrogen | At least 66 % of approved projects started | 2024-06-30 | Completed | FALSE
2019.CSR3.subpart1 | IPCEI Hydrogen | EUR 125 000 000 have been committed to the approved projects | 2025-12-31 | Not completed | FALSE
2020.CSR3.subpart5 | IPCEI Hydrogen | EUR 125 000 000 have been committed to the approved projects | 2025-12-31 | Not completed | FALSE
2022.CSR4.subpart1 | IPCEI Hydrogen | EUR 125 000 000 have been committed to the approved projects | 2025-12-31 | Not completed | FALSE
2022.CSR4.subpart2 | IPCEI Hydrogen | EUR 125 000 000 have been committed to the approved projects | 2025-12-31 | Not completed | FALSE
2023.CSR4.subpart1 | IPCEI Hydrogen | EUR 125 000 000 have been committed to the approved projects | 2025-12-31 | Not completed | FALSE
2023.CSR4.subpart2 | IPCEI Hydrogen | EUR 125 000 000 have been committed to the approved projects | 2025-12-31 | Not completed | FALSE
2023.CSR4.subpart3 | IPCEI Hydrogen | EUR 125 000 000 have been committed to the approved projects | 2025-12-31 | Not completed | FALSE
2024.CSR4.subpart1 | IPCEI Hydrogen | EUR 125 000 000 have been committed to the approved projects | 2025-12-31 | Not completed | FALSE
2019.CSR3.subpart1 | RTI Strategy 2030 | Finalisation of perfor-mance and financing agreements | 2024-12-31 | On track | FALSE
2020.CSR3.subpart5 | RTI Strategy 2030 | Finalisation of perfor-mance and financing agreements | 2024-12-31 | On track | FALSE
2019.CSR3.subpart1 | RTI Strategy 2030 | Approval of the third RTI Pact | 2025-12-31 | Not completed | FALSE
2020.CSR3.subpart5 | RTI Strategy 2030 | Approval of the third RTI Pact | 2025-12-31 | Not completed | FALSE
2019.CSR3.subpart1 | Quantum Austria — Promotion of Quantum Sciences | Call for expressions of interest (BMBWF); Identification of an executing agency | 2021-12-31 | Fulfilled | FALSE
2020.CSR3.subpart5 | Quantum Austria — Promotion of Quantum Sciences | Call for expressions of interest (BMBWF); Identification of an executing agency | 2021-12-31 | Fulfilled | FALSE
2019.CSR3.subpart1 | Quantum Austria — Promotion of Quantum Sciences | Interim report | 2024-12-31 | On track | FALSE
2020.CSR3.subpart5 | Quantum Austria — Promotion of Quantum Sciences | Interim report | 2024-12-31 | On track | FALSE
2019.CSR3.subpart1 | Quantum Austria — Promotion of Quantum Sciences | Closure of projects with transfer to university operations | 2026-03-31 | Not completed | FALSE
2020.CSR3.subpart5 | Quantum Austria — Promotion of Quantum Sciences | Closure of projects with transfer to university operations | 2026-03-31 | Not completed | FALSE
2019.CSR3.subpart1 | Austrian Institute of Precision Medicine | Ministerial planning approval (BMBWF & BMF) | 2022-06-28 | Completed | FALSE
2020.CSR3.subpart5 | Austrian Institute of Precision Medicine | Ministerial planning approval (BMBWF & BMF) | 2022-06-28 | Completed | FALSE
2019.CSR3.subpart1 | Austrian Institute of Precision Medicine | Start of construction of the Institute of Precision Medicine | 2023-12-31 | Completed | FALSE
2020.CSR3.subpart5 | Austrian Institute of Precision Medicine | Start of construction of the Institute of Precision Medicine | 2023-12-31 | Completed | FALSE
2019.CSR3.subpart1 | (Digital) Research Infrastructures | Award decision for grants to universities investing in digital research infrastructure | 2022-12-31 | Completed | FALSE
2020.CSR3.subpart5 | (Digital) Research Infrastructures | Award decision for grants to universities investing in digital research infrastructure | 2022-12-31 | Completed | FALSE
2019.CSR3.subpart1 | (Digital) Research Infrastructures | Progress report with 50 % of investments completed | 2025-09-30 | On track | FALSE
2020.CSR3.subpart5 | (Digital) Research Infrastructures | Progress report with 50 % of investments completed | 2025-09-30 | On track | FALSE
2019.CSR3.subpart2 | Set-up of Platform Internet-infrastructure Austria (PIA) 2030 | Work programme of Platform Internet-infrastructure Austria (PIA 2030) to coordinate the interaction of all relevant stakeholders | 2021-12-30 | Fulfilled | FALSE
2019.CSR3.subpart2 | Set-up of Platform Internet-infrastructure Austria (PIA) 2030 | Implementation of the measures developed by the Platform to reduce red tape and simplify procedures for broadband deployment | 2023-12-31 | Completed | FALSE
2019.CSR3.subpart2 | Widespread availability of Gigabit capable access networks and creation of new symmetric Gigabit connections | Calls for tenders to enable Gigabit capable access networks completed | 2022-09-30 | Completed | FALSE
2020.CSR3.subpart3 | Widespread availability of Gigabit capable access networks and creation of new symmetric Gigabit connections | Calls for tenders to enable Gigabit capable access networks completed | 2022-09-30 | Completed | FALSE
2019.CSR3.subpart2 | Widespread availability of Gigabit capable access networks and creation of new symmetric Gigabit connections | Signature of contracts | 2023-09-30 | Completed | FALSE
2020.CSR3.subpart3 | Widespread availability of Gigabit capable access networks and creation of new symmetric Gigabit connections | Signature of contracts | 2023-09-30 | Completed | FALSE
2019.CSR3.subpart2 | Fair and equal access of pupils to basic digital competence | Entry into force of the School Digitalisation Act | 2021-03-30 | Fulfilled | FALSE
2020.CSR2.subpart1 | Fair and equal access of pupils to basic digital competence | Entry into force of the School Digitalisation Act | 2021-03-30 | Fulfilled | FALSE
2024.CSR3.subpart2 | Fair and equal access of pupils to basic digital competence | Entry into force of the School Digitalisation Act | 2021-03-30 | Fulfilled | FALSE
2019.CSR3.subpart2 | Fair and equal access of pupils to basic digital competence | Entry into force of the Implementing regulation | 2021-09-28 | Fulfilled | FALSE
2020.CSR2.subpart1 | Fair and equal access of pupils to basic digital competence | Entry into force of the Implementing regulation | 2021-09-28 | Fulfilled | FALSE
2024.CSR3.subpart2 | Fair and equal access of pupils to basic digital competence | Entry into force of the Implementing regulation | 2021-09-28 | Fulfilled | FALSE
2019.CSR3.subpart2 | Fair and equal access of pupils to basic digital competence | Evaluation of the School Digitalisation Act | 2025-06-30 | On track | FALSE
2020.CSR2.subpart1 | Fair and equal access of pupils to basic digital competence | Evaluation of the School Digitalisation Act | 2025-06-30 | On track | FALSE
2024.CSR3.subpart2 | Fair and equal access of pupils to basic digital competence | Evaluation of the School Digitalisation Act | 2025-06-30 | On track | FALSE
2019.CSR3.subpart2 | Provision of digital end-user devices to pupils | Award decision on tender regarding digital end devices | 2021-06-30 | Fulfilled | FALSE
2020.CSR2.subpart2 | Provision of digital end-user devices to pupils | Award decision on tender regarding digital end devices | 2021-06-30 | Fulfilled | FALSE
2024.CSR3.subpart2 | Provision of digital end-user devices to pupils | Award decision on tender regarding digital end devices | 2021-06-30 | Fulfilled | FALSE
2019.CSR3.subpart2 | Provision of digital end-user devices to pupils | Digital devices for the first two year of secondary school | 2021-12-31 | Fulfilled | FALSE
2020.CSR2.subpart2 | Provision of digital end-user devices to pupils | Digital devices for the first two year of secondary school | 2021-12-31 | Fulfilled | FALSE
2024.CSR3.subpart2 | Provision of digital end-user devices to pupils | Digital devices for the first two year of secondary school | 2021-12-31 | Fulfilled | FALSE
2019.CSR3.subpart2 | Provision of digital end-user devices to pupils | Digital devices for pupils in the lower secondary school level | 2025-06-30 | On track | FALSE
2020.CSR2.subpart2 | Provision of digital end-user devices to pupils | Digital devices for pupils in the lower secondary school level | 2025-06-30 | On track | FALSE
2024.CSR3.subpart2 | Provision of digital end-user devices to pupils | Digital devices for pupils in the lower secondary school level | 2025-06-30 | On track | FALSE
2019.CSR3.subpart2 | Proposed legislation for Once Only. Amendment of the Business Service Portal Act | Entry into force of the law amending the Business Service Portal Act; upgrade of the relevant IT infrastructure. | 2021-09-28 | Fulfilled | FALSE
2020.CSR3.subpart2 | Proposed legislation for Once Only. Amendment of the Business Service Portal Act | Entry into force of the law amending the Business Service Portal Act; upgrade of the relevant IT infrastructure. | 2021-09-28 | Fulfilled | FALSE
2024.CSR3.subpart3 | Proposed legislation for Once Only. Amendment of the Business Service Portal Act | Entry into force of the law amending the Business Service Portal Act; upgrade of the relevant IT infrastructure. | 2021-09-28 | Fulfilled | FALSE
2019.CSR3.subpart2 | Proposed legislation for Once Only. Amendment of the Business Service Portal Act | Linking registries to the Register and Systems Network (RSV), preparation of Single Digital Gateway (SDG), start of the Information Obligation Database (IVDB) by Ministries | 2022-12-31 | Completed | FALSE
2020.CSR3.subpart2 | Proposed legislation for Once Only. Amendment of the Business Service Portal Act | Linking registries to the Register and Systems Network (RSV), preparation of Single Digital Gateway (SDG), start of the Information Obligation Database (IVDB) by Ministries | 2022-12-31 | Completed | FALSE
2024.CSR3.subpart3 | Proposed legislation for Once Only. Amendment of the Business Service Portal Act | Linking registries to the Register and Systems Network (RSV), preparation of Single Digital Gateway (SDG), start of the Information Obligation Database (IVDB) by Ministries | 2022-12-31 | Completed | FALSE
2019.CSR3.subpart2 | Proposed legislation for Once Only. Amendment of the Business Service Portal Act | Establishing the Once Only technical system connection | 2024-08-31 | Completed | FALSE
2020.CSR3.subpart2 | Proposed legislation for Once Only. Amendment of the Business Service Portal Act | Establishing the Once Only technical system connection | 2024-08-31 | Completed | FALSE
2024.CSR3.subpart3 | Proposed legislation for Once Only. Amendment of the Business Service Portal Act | Establishing the Once Only technical system connection | 2024-08-31 | Completed | FALSE
2019.CSR3.subpart2 | Digitalisation fund public administration | Entry into force of the Digitalisation Fund Act | 2021-06-30 | Fulfilled | FALSE
2020.CSR3.subpart2 | Digitalisation fund public administration | Entry into force of the Digitalisation Fund Act | 2021-06-30 | Fulfilled | FALSE
2019.CSR3.subpart2 | Digitalisation fund public administration | Projects selected | 2022-06-30 | Completed | FALSE
2020.CSR3.subpart2 | Digitalisation fund public administration | Projects selected | 2022-06-30 | Completed | FALSE
2019.CSR3.subpart2 | Digitalisation fund public administration | Completion of the funded projects regarding digitalisation of public administration | 2024-08-31 | Completed | FALSE
2020.CSR3.subpart2 | Digitalisation fund public administration | Completion of the funded projects regarding digitalisation of public administration | 2024-08-31 | Completed | FALSE
2019.CSR3.subpart2 | Develop a national digitalisation strategy for cultural heritage | Launch of the consultation process on a strategy for the digitisation of cultural heritage | 2022-03-30 | Completed | FALSE
2019.CSR3.subpart2 | Develop a national digitalisation strategy for cultural heritage | Decision of the Ministry for Culture (BMOESK) on the strategy for the digitalisation of cultural heritage | 2023-03-31 | Completed | FALSE
2019.CSR3.subpart2 | Digitalisation wave cultural heritage | ‘Kulturpool pool Neu’ — web-based data aggregation platform from different cultural heritage institutions | 2023-03-31 | Completed | FALSE
2019.CSR3.subpart2 | Digitalisation wave cultural heritage | Cultural and art objects digitalisation programme | 2024-12-31 | On track | FALSE
2019.CSR3.subpart3 | Soil protection strategy | Adoption of a road map for the Austrian soil protection strategy | 2021-12-30 | Fulfilled | FALSE
2019.CSR3.subpart3 | Soil protection strategy | Adoption of the Austrian quantitative soil protection strategy | 2024-07-31 | Completed | FALSE
2019.CSR3.subpart3 | Investment in climate-friendly town centres | Adoption of the funding guidelines for the four areas of intervention | 2021-09-28 | Fulfilled | FALSE
2020.CSR3.subpart7 | Investment in climate-friendly town centres | Adoption of the funding guidelines for the four areas of intervention | 2021-09-28 | Fulfilled | FALSE
2022.CSR4.subpart1 | Investment in climate-friendly town centres | Adoption of the funding guidelines for the four areas of intervention | 2021-09-28 | Fulfilled | FALSE
2022.CSR4.subpart2 | Investment in climate-friendly town centres | Adoption of the funding guidelines for the four areas of intervention | 2021-09-28 | Fulfilled | FALSE
2022.CSR4.subpart3 | Investment in climate-friendly town centres | Adoption of the funding guidelines for the four areas of intervention | 2021-09-28 | Fulfilled | FALSE
2023.CSR4.subpart1 | Investment in climate-friendly town centres | Adoption of the funding guidelines for the four areas of intervention | 2021-09-28 | Fulfilled | FALSE
2023.CSR4.subpart3 | Investment in climate-friendly town centres | Adoption of the funding guidelines for the four areas of intervention | 2021-09-28 | Fulfilled | FALSE
2023.CSR4.subpart4 | Investment in climate-friendly town centres | Adoption of the funding guidelines for the four areas of intervention | 2021-09-28 | Fulfilled | FALSE
2024.CSR4.subpart1 | Investment in climate-friendly town centres | Adoption of the funding guidelines for the four areas of intervention | 2021-09-28 | Fulfilled | FALSE
2019.CSR3.subpart3 | Investment in climate-friendly town centres | Thermal refurbishment projects completed | 2024-08-31 | Completed | FALSE
2020.CSR3.subpart7 | Investment in climate-friendly town centres | Thermal refurbishment projects completed | 2024-08-31 | Completed | FALSE
2022.CSR4.subpart1 | Investment in climate-friendly town centres | Thermal refurbishment projects completed | 2024-08-31 | Completed | FALSE
2022.CSR4.subpart2 | Investment in climate-friendly town centres | Thermal refurbishment projects completed | 2024-08-31 | Completed | FALSE
2022.CSR4.subpart3 | Investment in climate-friendly town centres | Thermal refurbishment projects completed | 2024-08-31 | Completed | FALSE
2023.CSR4.subpart1 | Investment in climate-friendly town centres | Thermal refurbishment projects completed | 2024-08-31 | Completed | FALSE
2023.CSR4.subpart3 | Investment in climate-friendly town centres | Thermal refurbishment projects completed | 2024-08-31 | Completed | FALSE
2023.CSR4.subpart4 | Investment in climate-friendly town centres | Thermal refurbishment projects completed | 2024-08-31 | Completed | FALSE
2024.CSR4.subpart1 | Investment in climate-friendly town centres | Thermal refurbishment projects completed | 2024-08-31 | Completed | FALSE
2019.CSR3.subpart3 | Investment in climate-friendly town centres | Projects for the connection to high-efficiency district heating completed | 2023-12-31 | Completed | FALSE
2020.CSR3.subpart7 | Investment in climate-friendly town centres | Projects for the connection to high-efficiency district heating completed | 2023-12-31 | Completed | FALSE
2022.CSR4.subpart1 | Investment in climate-friendly town centres | Projects for the connection to high-efficiency district heating completed | 2023-12-31 | Completed | FALSE
2022.CSR4.subpart2 | Investment in climate-friendly town centres | Projects for the connection to high-efficiency district heating completed | 2023-12-31 | Completed | FALSE
2022.CSR4.subpart3 | Investment in climate-friendly town centres | Projects for the connection to high-efficiency district heating completed | 2023-12-31 | Completed | FALSE
2023.CSR4.subpart1 | Investment in climate-friendly town centres | Projects for the connection to high-efficiency district heating completed | 2023-12-31 | Completed | FALSE
2023.CSR4.subpart3 | Investment in climate-friendly town centres | Projects for the connection to high-efficiency district heating completed | 2023-12-31 | Completed | FALSE
2023.CSR4.subpart4 | Investment in climate-friendly town centres | Projects for the connection to high-efficiency district heating completed | 2023-12-31 | Completed | FALSE
2024.CSR4.subpart1 | Investment in climate-friendly town centres | Projects for the connection to high-efficiency district heating completed | 2023-12-31 | Completed | FALSE
2019.CSR3.subpart3 | Investment in climate-friendly town centres | Brownfield land projects completed | 2024-08-31 | Completed | FALSE
2020.CSR3.subpart7 | Investment in climate-friendly town centres | Brownfield land projects completed | 2024-08-31 | Completed | FALSE
2022.CSR4.subpart1 | Investment in climate-friendly town centres | Brownfield land projects completed | 2024-08-31 | Completed | FALSE
2022.CSR4.subpart2 | Investment in climate-friendly town centres | Brownfield land projects completed | 2024-08-31 | Completed | FALSE
2022.CSR4.subpart3 | Investment in climate-friendly town centres | Brownfield land projects completed | 2024-08-31 | Completed | FALSE
2023.CSR4.subpart1 | Investment in climate-friendly town centres | Brownfield land projects completed | 2024-08-31 | Completed | FALSE
2023.CSR4.subpart3 | Investment in climate-friendly town centres | Brownfield land projects completed | 2024-08-31 | Completed | FALSE
2023.CSR4.subpart4 | Investment in climate-friendly town centres | Brownfield land projects completed | 2024-08-31 | Completed | FALSE
2024.CSR4.subpart1 | Investment in climate-friendly town centres | Brownfield land projects completed | 2024-08-31 | Completed | FALSE
2019.CSR3.subpart3 | Development of a building culture programme | Fourth Building Culture report | 2021-09-28 | Fulfilled | FALSE
2020.CSR3.subpart7 | Development of a building culture programme | Fourth Building Culture report | 2021-09-28 | Fulfilled | FALSE
2019.CSR3.subpart3 | Renovation Volkskundemuseum Wien and Prater Ateliers | Feasibility studies for the Volkskundemuseum Wien and Prater Ateliers | 2021-12-29 | Fulfilled | FALSE
2020.CSR3.subpart7 | Renovation Volkskundemuseum Wien and Prater Ateliers | Feasibility studies for the Volkskundemuseum Wien and Prater Ateliers | 2021-12-29 | Fulfilled | FALSE
2023.CSR4.subpart1 | Renovation Volkskundemuseum Wien and Prater Ateliers | Feasibility studies for the Volkskundemuseum Wien and Prater Ateliers | 2021-12-29 | Fulfilled | FALSE
2023.CSR4.subpart4 | Renovation Volkskundemuseum Wien and Prater Ateliers | Feasibility studies for the Volkskundemuseum Wien and Prater Ateliers | 2021-12-29 | Fulfilled | FALSE
2019.CSR3.subpart3 | Renovation Volkskundemuseum Wien and Prater Ateliers | Reopening of Prater Ateliers | 2025-06-30 | On track | FALSE
2020.CSR3.subpart7 | Renovation Volkskundemuseum Wien and Prater Ateliers | Reopening of Prater Ateliers | 2025-06-30 | On track | FALSE
2023.CSR4.subpart1 | Renovation Volkskundemuseum Wien and Prater Ateliers | Reopening of Prater Ateliers | 2025-06-30 | On track | FALSE
2023.CSR4.subpart4 | Renovation Volkskundemuseum Wien and Prater Ateliers | Reopening of Prater Ateliers | 2025-06-30 | On track | FALSE
2019.CSR3.subpart3 | Investment fund for climate-friendly cultural businesses | Entry into force of the funding guidelines establishing the investment fund | 2021-12-31 | Fulfilled | FALSE
2020.CSR3.subpart7 | Investment fund for climate-friendly cultural businesses | Entry into force of the funding guidelines establishing the investment fund | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart1 | Investment fund for climate-friendly cultural businesses | Entry into force of the funding guidelines establishing the investment fund | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart2 | Investment fund for climate-friendly cultural businesses | Entry into force of the funding guidelines establishing the investment fund | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart3 | Investment fund for climate-friendly cultural businesses | Entry into force of the funding guidelines establishing the investment fund | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart1 | Investment fund for climate-friendly cultural businesses | Entry into force of the funding guidelines establishing the investment fund | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart3 | Investment fund for climate-friendly cultural businesses | Entry into force of the funding guidelines establishing the investment fund | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart4 | Investment fund for climate-friendly cultural businesses | Entry into force of the funding guidelines establishing the investment fund | 2021-12-31 | Fulfilled | FALSE
2024.CSR4.subpart1 | Investment fund for climate-friendly cultural businesses | Entry into force of the funding guidelines establishing the investment fund | 2021-12-31 | Fulfilled | FALSE
2019.CSR3.subpart3 | Investment fund for climate-friendly cultural businesses | First call for expressions of interest | 2022-06-30 | Completed | FALSE
2020.CSR3.subpart7 | Investment fund for climate-friendly cultural businesses | First call for expressions of interest | 2022-06-30 | Completed | FALSE
2022.CSR4.subpart1 | Investment fund for climate-friendly cultural businesses | First call for expressions of interest | 2022-06-30 | Completed | FALSE
2022.CSR4.subpart2 | Investment fund for climate-friendly cultural businesses | First call for expressions of interest | 2022-06-30 | Completed | FALSE
2022.CSR4.subpart3 | Investment fund for climate-friendly cultural businesses | First call for expressions of interest | 2022-06-30 | Completed | FALSE
2023.CSR4.subpart1 | Investment fund for climate-friendly cultural businesses | First call for expressions of interest | 2022-06-30 | Completed | FALSE
2023.CSR4.subpart3 | Investment fund for climate-friendly cultural businesses | First call for expressions of interest | 2022-06-30 | Completed | FALSE
2023.CSR4.subpart4 | Investment fund for climate-friendly cultural businesses | First call for expressions of interest | 2022-06-30 | Completed | FALSE
2024.CSR4.subpart1 | Investment fund for climate-friendly cultural businesses | First call for expressions of interest | 2022-06-30 | Completed | FALSE
2019.CSR3.subpart3 | Investment fund for climate-friendly cultural businesses | Contract award of climate-friendly cultural businesses projects | 2025-09-30 | On track | FALSE
2020.CSR3.subpart7 | Investment fund for climate-friendly cultural businesses | Contract award of climate-friendly cultural businesses projects | 2025-09-30 | On track | FALSE
2022.CSR4.subpart1 | Investment fund for climate-friendly cultural businesses | Contract award of climate-friendly cultural businesses projects | 2025-09-30 | On track | FALSE
2022.CSR4.subpart2 | Investment fund for climate-friendly cultural businesses | Contract award of climate-friendly cultural businesses projects | 2025-09-30 | On track | FALSE
2022.CSR4.subpart3 | Investment fund for climate-friendly cultural businesses | Contract award of climate-friendly cultural businesses projects | 2025-09-30 | On track | FALSE
2023.CSR4.subpart1 | Investment fund for climate-friendly cultural businesses | Contract award of climate-friendly cultural businesses projects | 2025-09-30 | On track | FALSE
2023.CSR4.subpart3 | Investment fund for climate-friendly cultural businesses | Contract award of climate-friendly cultural businesses projects | 2025-09-30 | On track | FALSE
2023.CSR4.subpart4 | Investment fund for climate-friendly cultural businesses | Contract award of climate-friendly cultural businesses projects | 2025-09-30 | On track | FALSE
2024.CSR4.subpart1 | Investment fund for climate-friendly cultural businesses | Contract award of climate-friendly cultural businesses projects | 2025-09-30 | On track | FALSE
2019.CSR3.subpart3 | Climate action governance framework | Citizens’ Climate Council (Klimarat) and focal point on green budgeting | 2021-12-30 | Fulfilled | FALSE
2020.CSR3.subpart5 | Climate action governance framework | Citizens’ Climate Council (Klimarat) and focal point on green budgeting | 2021-12-30 | Fulfilled | FALSE
2019.CSR3.subpart3 | Climate action governance framework | Entry into force of a law introducing a mandatory climate check for new legislative proposals | 2022-06-30 | Not completed | FALSE
2020.CSR3.subpart5 | Climate action governance framework | Entry into force of a law introducing a mandatory climate check for new legislative proposals | 2022-06-30 | Not completed | FALSE
2019.CSR3.subpart3 | Green Finance (Agenda) | Green Finance Agenda | 2023-09-30 | Completed | FALSE
2020.CSR3.subpart5 | Green Finance (Agenda) | Green Finance Agenda | 2023-09-30 | Completed | FALSE
2024.CSR1.subpart7 | Green Finance (Agenda) | Green Finance Agenda | 2023-09-30 | Completed | FALSE
2019.CSR3.subpart3 | Green Finance (Agenda) | Use of quantitative and qualitative indicators to measure the achievement of implementation | 2024-05-31 | Completed | FALSE
2020.CSR3.subpart5 | Green Finance (Agenda) | Use of quantitative and qualitative indicators to measure the achievement of implementation | 2024-05-31 | Completed | FALSE
2024.CSR1.subpart7 | Green Finance (Agenda) | Use of quantitative and qualitative indicators to measure the achievement of implementation | 2024-05-31 | Completed | FALSE
2019.CSR3.subpart3 | Acceleration of permitting procedures for renewables | Entry into force of the amended EIA Act | 2023-03-31 | Completed | TRUE
2020.CSR3.subpart7 | Acceleration of permitting procedures for renewables | Entry into force of the amended EIA Act | 2023-03-31 | Completed | TRUE
2022.CSR4.subpart2 | Acceleration of permitting procedures for renewables | Entry into force of the amended EIA Act | 2023-03-31 | Completed | TRUE
2023.CSR4.subpart1 | Acceleration of permitting procedures for renewables | Entry into force of the amended EIA Act | 2023-03-31 | Completed | TRUE
2023.CSR4.subpart3 | Acceleration of permitting procedures for renewables | Entry into force of the amended EIA Act | 2023-03-31 | Completed | TRUE
2024.CSR4.subpart1 | Acceleration of permitting procedures for renewables | Entry into force of the amended EIA Act | 2023-03-31 | Completed | TRUE
2019.CSR3.subpart3 | Acceleration of permitting procedures for renewables | 9th EIA Report presented to Parliament | 2024-09-30 | Completed | TRUE
2020.CSR3.subpart7 | Acceleration of permitting procedures for renewables | 9th EIA Report presented to Parliament | 2024-09-30 | Completed | TRUE
2022.CSR4.subpart2 | Acceleration of permitting procedures for renewables | 9th EIA Report presented to Parliament | 2024-09-30 | Completed | TRUE
2023.CSR4.subpart1 | Acceleration of permitting procedures for renewables | 9th EIA Report presented to Parliament | 2024-09-30 | Completed | TRUE
2023.CSR4.subpart3 | Acceleration of permitting procedures for renewables | 9th EIA Report presented to Parliament | 2024-09-30 | Completed | TRUE
2024.CSR4.subpart1 | Acceleration of permitting procedures for renewables | 9th EIA Report presented to Parliament | 2024-09-30 | Completed | TRUE
2019.CSR3.subpart3 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2020.CSR3.subpart5 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2022.CSR4.subpart1 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2022.CSR4.subpart2 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2022.CSR4.subpart3 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2023.CSR4.subpart1 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2023.CSR4.subpart2 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2023.CSR4.subpart3 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2023.CSR4.subpart5 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2024.CSR4.subpart1 | Hydrogen as key technology to climate neutrality | The Hydrogen Strategy is adopted and the national hydrogen platform is established | 2023-06-30 | Completed | TRUE
2019.CSR3.subpart3 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2020.CSR3.subpart5 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2022.CSR4.subpart1 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2022.CSR4.subpart2 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2022.CSR4.subpart3 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2023.CSR4.subpart1 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2023.CSR4.subpart2 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2023.CSR4.subpart3 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2023.CSR4.subpart5 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2024.CSR4.subpart1 | Hydrogen as key technology to climate neutrality | Publication of the evaluation report | 2024-03-31 | Completed | TRUE
2019.CSR3.subpart3 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2020.CSR3.subpart5 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2022.CSR4.subpart1 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2022.CSR4.subpart2 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2022.CSR4.subpart3 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2023.CSR4.subpart1 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2023.CSR4.subpart2 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2023.CSR4.subpart3 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2023.CSR4.subpart5 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2024.CSR4.subpart1 | Hydrogen as key technology to climate neutrality | Implementation of two key measures in the Hydrogen Strategy | 2026-03-31 | Not completed | TRUE
2019.CSR3.subpart3 | Renewable Heating Law | Entry into force of Renewable Heating Law | 2022-03-31 | Completed | FALSE
2020.CSR3.subpart7 | Renewable Heating Law | Entry into force of Renewable Heating Law | 2022-03-31 | Completed | FALSE
2022.CSR4.subpart1 | Renewable Heating Law | Entry into force of Renewable Heating Law | 2022-03-31 | Completed | FALSE
2022.CSR4.subpart2 | Renewable Heating Law | Entry into force of Renewable Heating Law | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart1 | Renewable Heating Law | Entry into force of Renewable Heating Law | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart2 | Renewable Heating Law | Entry into force of Renewable Heating Law | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart3 | Renewable Heating Law | Entry into force of Renewable Heating Law | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart6 | Renewable Heating Law | Entry into force of Renewable Heating Law | 2022-03-31 | Completed | FALSE
2024.CSR4.subpart1 | Renewable Heating Law | Entry into force of Renewable Heating Law | 2022-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Renewable Heating Law | Training for energy consultants | 2022-12-31 | Completed | FALSE
2020.CSR3.subpart7 | Renewable Heating Law | Training for energy consultants | 2022-12-31 | Completed | FALSE
2022.CSR4.subpart1 | Renewable Heating Law | Training for energy consultants | 2022-12-31 | Completed | FALSE
2022.CSR4.subpart2 | Renewable Heating Law | Training for energy consultants | 2022-12-31 | Completed | FALSE
2023.CSR4.subpart1 | Renewable Heating Law | Training for energy consultants | 2022-12-31 | Completed | FALSE
2023.CSR4.subpart2 | Renewable Heating Law | Training for energy consultants | 2022-12-31 | Completed | FALSE
2023.CSR4.subpart3 | Renewable Heating Law | Training for energy consultants | 2022-12-31 | Completed | FALSE
2023.CSR4.subpart6 | Renewable Heating Law | Training for energy consultants | 2022-12-31 | Completed | FALSE
2024.CSR4.subpart1 | Renewable Heating Law | Training for energy consultants | 2022-12-31 | Completed | FALSE
2019.CSR3.subpart3 | Exchange of oil and gas heating systems | Replacement of heating systems | 2021-12-31 | Fulfilled | FALSE
2020.CSR3.subpart7 | Exchange of oil and gas heating systems | Replacement of heating systems | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart1 | Exchange of oil and gas heating systems | Replacement of heating systems | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart2 | Exchange of oil and gas heating systems | Replacement of heating systems | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart1 | Exchange of oil and gas heating systems | Replacement of heating systems | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart2 | Exchange of oil and gas heating systems | Replacement of heating systems | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart3 | Exchange of oil and gas heating systems | Replacement of heating systems | 2021-12-31 | Fulfilled | FALSE
2024.CSR4.subpart1 | Exchange of oil and gas heating systems | Replacement of heating systems | 2021-12-31 | Fulfilled | FALSE
2019.CSR3.subpart3 | Exchange of oil and gas heating systems | Replacement of heating systems | 2022-12-31 | Completed | FALSE
2020.CSR3.subpart7 | Exchange of oil and gas heating systems | Replacement of heating systems | 2022-12-31 | Completed | FALSE
2022.CSR4.subpart1 | Exchange of oil and gas heating systems | Replacement of heating systems | 2022-12-31 | Completed | FALSE
2022.CSR4.subpart2 | Exchange of oil and gas heating systems | Replacement of heating systems | 2022-12-31 | Completed | FALSE
2023.CSR4.subpart1 | Exchange of oil and gas heating systems | Replacement of heating systems | 2022-12-31 | Completed | FALSE
2023.CSR4.subpart2 | Exchange of oil and gas heating systems | Replacement of heating systems | 2022-12-31 | Completed | FALSE
2023.CSR4.subpart3 | Exchange of oil and gas heating systems | Replacement of heating systems | 2022-12-31 | Completed | FALSE
2024.CSR4.subpart1 | Exchange of oil and gas heating systems | Replacement of heating systems | 2022-12-31 | Completed | FALSE
2019.CSR3.subpart3 | Combating energy poverty | Determination of funding priorities | 2022-03-31 | Completed | FALSE
2020.CSR3.subpart7 | Combating energy poverty | Determination of funding priorities | 2022-03-31 | Completed | FALSE
2022.CSR4.subpart1 | Combating energy poverty | Determination of funding priorities | 2022-03-31 | Completed | FALSE
2022.CSR4.subpart2 | Combating energy poverty | Determination of funding priorities | 2022-03-31 | Completed | FALSE
2022.CSR4.subpart3 | Combating energy poverty | Determination of funding priorities | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart1 | Combating energy poverty | Determination of funding priorities | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart3 | Combating energy poverty | Determination of funding priorities | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart4 | Combating energy poverty | Determination of funding priorities | 2022-03-31 | Completed | FALSE
2024.CSR4.subpart1 | Combating energy poverty | Determination of funding priorities | 2022-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Combating energy poverty | Thermal renovation projects approved | 2024-06-30 | Completed | FALSE
2020.CSR3.subpart7 | Combating energy poverty | Thermal renovation projects approved | 2024-06-30 | Completed | FALSE
2022.CSR4.subpart1 | Combating energy poverty | Thermal renovation projects approved | 2024-06-30 | Completed | FALSE
2022.CSR4.subpart2 | Combating energy poverty | Thermal renovation projects approved | 2024-06-30 | Completed | FALSE
2022.CSR4.subpart3 | Combating energy poverty | Thermal renovation projects approved | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart1 | Combating energy poverty | Thermal renovation projects approved | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart3 | Combating energy poverty | Thermal renovation projects approved | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart4 | Combating energy poverty | Thermal renovation projects approved | 2024-06-30 | Completed | FALSE
2024.CSR4.subpart1 | Combating energy poverty | Thermal renovation projects approved | 2024-06-30 | Completed | FALSE
2019.CSR3.subpart3 | Mobility Masterplan 2030 | Implementation of the Mobility Masterplan has started | 2023-09-30 | Completed | FALSE
2020.CSR3.subpart6 | Mobility Masterplan 2030 | Implementation of the Mobility Masterplan has started | 2023-09-30 | Completed | FALSE
2022.CSR4.subpart1 | Mobility Masterplan 2030 | Implementation of the Mobility Masterplan has started | 2023-09-30 | Completed | FALSE
2022.CSR4.subpart2 | Mobility Masterplan 2030 | Implementation of the Mobility Masterplan has started | 2023-09-30 | Completed | FALSE
2023.CSR4.subpart1 | Mobility Masterplan 2030 | Implementation of the Mobility Masterplan has started | 2023-09-30 | Completed | FALSE
2023.CSR4.subpart3 | Mobility Masterplan 2030 | Implementation of the Mobility Masterplan has started | 2023-09-30 | Completed | FALSE
2023.CSR4.subpart5 | Mobility Masterplan 2030 | Implementation of the Mobility Masterplan has started | 2023-09-30 | Completed | FALSE
2024.CSR4.subpart1 | Mobility Masterplan 2030 | Implementation of the Mobility Masterplan has started | 2023-09-30 | Completed | FALSE
2024.CSR4.subpart2 | Mobility Masterplan 2030 | Implementation of the Mobility Masterplan has started | 2023-09-30 | Completed | FALSE
2019.CSR3.subpart3 | Mobility Masterplan 2030 | Reduction of CO₂ emissions in the transport sector | 2025-09-30 | On track | FALSE
2020.CSR3.subpart6 | Mobility Masterplan 2030 | Reduction of CO₂ emissions in the transport sector | 2025-09-30 | On track | FALSE
2022.CSR4.subpart1 | Mobility Masterplan 2030 | Reduction of CO₂ emissions in the transport sector | 2025-09-30 | On track | FALSE
2022.CSR4.subpart2 | Mobility Masterplan 2030 | Reduction of CO₂ emissions in the transport sector | 2025-09-30 | On track | FALSE
2023.CSR4.subpart1 | Mobility Masterplan 2030 | Reduction of CO₂ emissions in the transport sector | 2025-09-30 | On track | FALSE
2023.CSR4.subpart3 | Mobility Masterplan 2030 | Reduction of CO₂ emissions in the transport sector | 2025-09-30 | On track | FALSE
2023.CSR4.subpart5 | Mobility Masterplan 2030 | Reduction of CO₂ emissions in the transport sector | 2025-09-30 | On track | FALSE
2024.CSR4.subpart1 | Mobility Masterplan 2030 | Reduction of CO₂ emissions in the transport sector | 2025-09-30 | On track | FALSE
2024.CSR4.subpart2 | Mobility Masterplan 2030 | Reduction of CO₂ emissions in the transport sector | 2025-09-30 | On track | FALSE
2019.CSR3.subpart3 | Introduction of 1-2-3 climate ticket | Entry into force of law | 2021-09-28 | Fulfilled | FALSE
2020.CSR3.subpart6 | Introduction of 1-2-3 climate ticket | Entry into force of law | 2021-09-28 | Fulfilled | FALSE
2022.CSR4.subpart1 | Introduction of 1-2-3 climate ticket | Entry into force of law | 2021-09-28 | Fulfilled | FALSE
2023.CSR4.subpart1 | Introduction of 1-2-3 climate ticket | Entry into force of law | 2021-09-28 | Fulfilled | FALSE
2023.CSR4.subpart5 | Introduction of 1-2-3 climate ticket | Entry into force of law | 2021-09-28 | Fulfilled | FALSE
2024.CSR4.subpart1 | Introduction of 1-2-3 climate ticket | Entry into force of law | 2021-09-28 | Fulfilled | FALSE
2024.CSR4.subpart2 | Introduction of 1-2-3 climate ticket | Entry into force of law | 2021-09-28 | Fulfilled | FALSE
2019.CSR3.subpart3 | Introduction of 1-2-3 climate ticket | Introduction of 1-2-3 climate ticket | 2021-12-30 | Fulfilled | FALSE
2020.CSR3.subpart6 | Introduction of 1-2-3 climate ticket | Introduction of 1-2-3 climate ticket | 2021-12-30 | Fulfilled | FALSE
2022.CSR4.subpart1 | Introduction of 1-2-3 climate ticket | Introduction of 1-2-3 climate ticket | 2021-12-30 | Fulfilled | FALSE
2023.CSR4.subpart1 | Introduction of 1-2-3 climate ticket | Introduction of 1-2-3 climate ticket | 2021-12-30 | Fulfilled | FALSE
2023.CSR4.subpart5 | Introduction of 1-2-3 climate ticket | Introduction of 1-2-3 climate ticket | 2021-12-30 | Fulfilled | FALSE
2024.CSR4.subpart1 | Introduction of 1-2-3 climate ticket | Introduction of 1-2-3 climate ticket | 2021-12-30 | Fulfilled | FALSE
2024.CSR4.subpart2 | Introduction of 1-2-3 climate ticket | Introduction of 1-2-3 climate ticket | 2021-12-30 | Fulfilled | FALSE
2019.CSR3.subpart3 | Zero-emission buses | Launch of the zero-emission buses support programme | 2022-03-31 | Completed | FALSE
2020.CSR3.subpart6 | Zero-emission buses | Launch of the zero-emission buses support programme | 2022-03-31 | Completed | FALSE
2022.CSR4.subpart1 | Zero-emission buses | Launch of the zero-emission buses support programme | 2022-03-31 | Completed | FALSE
2022.CSR4.subpart2 | Zero-emission buses | Launch of the zero-emission buses support programme | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart1 | Zero-emission buses | Launch of the zero-emission buses support programme | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart3 | Zero-emission buses | Launch of the zero-emission buses support programme | 2022-03-31 | Completed | FALSE
2023.CSR4.subpart5 | Zero-emission buses | Launch of the zero-emission buses support programme | 2022-03-31 | Completed | FALSE
2024.CSR4.subpart1 | Zero-emission buses | Launch of the zero-emission buses support programme | 2022-03-31 | Completed | FALSE
2024.CSR4.subpart2 | Zero-emission buses | Launch of the zero-emission buses support programme | 2022-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Zero-emission buses | Last call completed | 2024-12-31 | On track | FALSE
2020.CSR3.subpart6 | Zero-emission buses | Last call completed | 2024-12-31 | On track | FALSE
2022.CSR4.subpart1 | Zero-emission buses | Last call completed | 2024-12-31 | On track | FALSE
2022.CSR4.subpart2 | Zero-emission buses | Last call completed | 2024-12-31 | On track | FALSE
2023.CSR4.subpart1 | Zero-emission buses | Last call completed | 2024-12-31 | On track | FALSE
2023.CSR4.subpart3 | Zero-emission buses | Last call completed | 2024-12-31 | On track | FALSE
2023.CSR4.subpart5 | Zero-emission buses | Last call completed | 2024-12-31 | On track | FALSE
2024.CSR4.subpart1 | Zero-emission buses | Last call completed | 2024-12-31 | On track | FALSE
2024.CSR4.subpart2 | Zero-emission buses | Last call completed | 2024-12-31 | On track | FALSE
2019.CSR3.subpart3 | Zero-emission utility vehicles | Launch of the support programme | 2021-03-31 | Fulfilled | FALSE
2020.CSR3.subpart6 | Zero-emission utility vehicles | Launch of the support programme | 2021-03-31 | Fulfilled | FALSE
2022.CSR4.subpart1 | Zero-emission utility vehicles | Launch of the support programme | 2021-03-31 | Fulfilled | FALSE
2022.CSR4.subpart2 | Zero-emission utility vehicles | Launch of the support programme | 2021-03-31 | Fulfilled | FALSE
2023.CSR4.subpart1 | Zero-emission utility vehicles | Launch of the support programme | 2021-03-31 | Fulfilled | FALSE
2023.CSR4.subpart3 | Zero-emission utility vehicles | Launch of the support programme | 2021-03-31 | Fulfilled | FALSE
2023.CSR4.subpart5 | Zero-emission utility vehicles | Launch of the support programme | 2021-03-31 | Fulfilled | FALSE
2024.CSR4.subpart1 | Zero-emission utility vehicles | Launch of the support programme | 2021-03-31 | Fulfilled | FALSE
2024.CSR4.subpart2 | Zero-emission utility vehicles | Launch of the support programme | 2021-03-31 | Fulfilled | FALSE
2019.CSR3.subpart3 | Zero-emission utility vehicles | Last call completed | 2024-12-31 | Completed | FALSE
2020.CSR3.subpart6 | Zero-emission utility vehicles | Last call completed | 2024-12-31 | Completed | FALSE
2022.CSR4.subpart1 | Zero-emission utility vehicles | Last call completed | 2024-12-31 | Completed | FALSE
2022.CSR4.subpart2 | Zero-emission utility vehicles | Last call completed | 2024-12-31 | Completed | FALSE
2023.CSR4.subpart1 | Zero-emission utility vehicles | Last call completed | 2024-12-31 | Completed | FALSE
2023.CSR4.subpart3 | Zero-emission utility vehicles | Last call completed | 2024-12-31 | Completed | FALSE
2023.CSR4.subpart5 | Zero-emission utility vehicles | Last call completed | 2024-12-31 | Completed | FALSE
2024.CSR4.subpart1 | Zero-emission utility vehicles | Last call completed | 2024-12-31 | Completed | FALSE
2024.CSR4.subpart2 | Zero-emission utility vehicles | Last call completed | 2024-12-31 | Completed | FALSE
2019.CSR3.subpart3 | Construction of new railways and electrification of regional railways | Ongoing construction project | 2020-03-30 | Fulfilled | FALSE
2020.CSR3.subpart6 | Construction of new railways and electrification of regional railways | Ongoing construction project | 2020-03-30 | Fulfilled | FALSE
2022.CSR4.subpart1 | Construction of new railways and electrification of regional railways | Ongoing construction project | 2020-03-30 | Fulfilled | FALSE
2023.CSR4.subpart1 | Construction of new railways and electrification of regional railways | Ongoing construction project | 2020-03-30 | Fulfilled | FALSE
2023.CSR4.subpart5 | Construction of new railways and electrification of regional railways | Ongoing construction project | 2020-03-30 | Fulfilled | FALSE
2024.CSR4.subpart1 | Construction of new railways and electrification of regional railways | Ongoing construction project | 2020-03-30 | Fulfilled | FALSE
2024.CSR4.subpart2 | Construction of new railways and electrification of regional railways | Ongoing construction project | 2020-03-30 | Fulfilled | FALSE
2019.CSR3.subpart3 | Construction of new railways and electrification of regional railways | Electrification | 2023-12-31 | Completed | FALSE
2020.CSR3.subpart6 | Construction of new railways and electrification of regional railways | Electrification | 2023-12-31 | Completed | FALSE
2022.CSR4.subpart1 | Construction of new railways and electrification of regional railways | Electrification | 2023-12-31 | Completed | FALSE
2023.CSR4.subpart1 | Construction of new railways and electrification of regional railways | Electrification | 2023-12-31 | Completed | FALSE
2023.CSR4.subpart5 | Construction of new railways and electrification of regional railways | Electrification | 2023-12-31 | Completed | FALSE
2024.CSR4.subpart1 | Construction of new railways and electrification of regional railways | Electrification | 2023-12-31 | Completed | FALSE
2024.CSR4.subpart2 | Construction of new railways and electrification of regional railways | Electrification | 2023-12-31 | Completed | FALSE
2019.CSR3.subpart3 | Construction of new railways and electrification of regional railways | Completion of construction project | 2025-12-31 | Not completed | FALSE
2020.CSR3.subpart6 | Construction of new railways and electrification of regional railways | Completion of construction project | 2025-12-31 | Not completed | FALSE
2022.CSR4.subpart1 | Construction of new railways and electrification of regional railways | Completion of construction project | 2025-12-31 | Not completed | FALSE
2023.CSR4.subpart1 | Construction of new railways and electrification of regional railways | Completion of construction project | 2025-12-31 | Not completed | FALSE
2023.CSR4.subpart5 | Construction of new railways and electrification of regional railways | Completion of construction project | 2025-12-31 | Not completed | FALSE
2024.CSR4.subpart1 | Construction of new railways and electrification of regional railways | Completion of construction project | 2025-12-31 | Not completed | FALSE
2024.CSR4.subpart2 | Construction of new railways and electrification of regional railways | Completion of construction project | 2025-12-31 | Not completed | FALSE
2019.CSR3.subpart3 | Legal framework for increasing collection rates for beverage packaging and the supply of reusable beverage containers in retail | Entry into force of the amended Waste Management Act | 2021-12-30 | Fulfilled | FALSE
2019.CSR3.subpart3 | Legal framework for increasing collection rates for beverage packaging and the supply of reusable beverage containers in retail | Entry into force of the implementing regulation | 2023-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Legal framework for increasing collection rates for beverage packaging and the supply of reusable beverage containers in retail | Reusable quota | 2026-03-31 | Not completed | FALSE
2019.CSR3.subpart3 | Biodiversity fund | Entry into force of the legal framework for Biodiversity Fund | 2022-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Biodiversity fund | Completion of the call for projects to restore priority degraded ecosystems and protect endangered species and habitats | 2023-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Biodiversity fund | Biodiversity projects completed | 2025-12-31 | Not completed | FALSE
2019.CSR3.subpart3 | Investments in reverse vending systems and measures to increase the reuse quota of beverage containers | Take-back systems | 2024-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Investments in reverse vending systems and measures to increase the reuse quota of beverage containers | Increased collection rate | 2026-03-31 | Not completed | FALSE
2019.CSR3.subpart3 | Retrofitting of existing and construction of new sorting facilities | Permit applications for construction or retrofitting | 2022-09-30 | Completed | FALSE
2019.CSR3.subpart3 | Retrofitting of existing and construction of new sorting facilities | Commissioning of facilities | 2025-03-31 | Delayed | FALSE
2019.CSR3.subpart3 | Retrofitting of existing and construction of new sorting facilities | Sorting depth | 2026-03-31 | Not completed | FALSE
2019.CSR3.subpart3 | Promotion of the repairing of electrical and electronic equipment (repair bonus) | Launch of the repair bonus support programme | 2022-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Promotion of the repairing of electrical and electronic equipment (repair bonus) | Repaired or renewed electrical or electronic equipment | 2024-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Promotion of the repairing of electrical and electronic equipment (repair bonus) | Increased number of repaired or renewed electrical or electronic equipment | 2026-03-31 | Not completed | FALSE
2019.CSR3.subpart3 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2020.CSR3.subpart7 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart1 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart2 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart3 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2022.CSR4.subpart4 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart1 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart2 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2023.CSR4.subpart3 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2024.CSR4.subpart1 | Renewables Expansion Law | Entry into force of the Renewables Expansion Law | 2021-12-31 | Fulfilled | FALSE
2019.CSR3.subpart3 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2020.CSR3.subpart7 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2022.CSR4.subpart1 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2022.CSR4.subpart2 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2022.CSR4.subpart3 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2022.CSR4.subpart4 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2023.CSR4.subpart1 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2023.CSR4.subpart2 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2023.CSR4.subpart3 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2024.CSR4.subpart1 | Renewables Expansion Law | Additional renewable electricity generation capacity | 2024-12-31 | Completed | FALSE
2019.CSR3.subpart3 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2020.CSR3.subpart7 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2022.CSR4.subpart1 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2022.CSR4.subpart2 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2022.CSR4.subpart3 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2023.CSR4.subpart1 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2023.CSR4.subpart2 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2023.CSR4.subpart3 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2023.CSR4.subpart4 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2024.CSR4.subpart1 | Transforming industry towards climate neutrality | Adoption of regulatory criteria and funding guidelines | 2021-09-30 | Fulfilled | FALSE
2019.CSR3.subpart3 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2020.CSR3.subpart7 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2022.CSR4.subpart1 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2022.CSR4.subpart2 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2022.CSR4.subpart3 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart1 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart2 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart3 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2023.CSR4.subpart4 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2024.CSR4.subpart1 | Transforming industry towards climate neutrality | Roll-out of decarbonisation projects | 2024-06-30 | Completed | FALSE
2019.CSR3.subpart3 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2020.CSR3.subpart4 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2020.CSR3.subpart7 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2022.CSR4.subpart1 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2022.CSR4.subpart2 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2022.CSR4.subpart3 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2023.CSR4.subpart1 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2023.CSR4.subpart3 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2023.CSR4.subpart4 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2024.CSR3.subpart3 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2024.CSR4.subpart1 | Green investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-29 | Fulfilled | FALSE
2019.CSR3.subpart3 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2020.CSR3.subpart4 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2020.CSR3.subpart7 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2022.CSR4.subpart1 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2022.CSR4.subpart2 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2022.CSR4.subpart3 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2023.CSR4.subpart1 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2023.CSR4.subpart3 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2023.CSR4.subpart4 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2024.CSR3.subpart3 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2024.CSR4.subpart1 | Green investments in enterprises | Investments in e-mobility | 2023-12-31 | Completed | FALSE
2019.CSR3.subpart3 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2020.CSR3.subpart4 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2020.CSR3.subpart7 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2022.CSR4.subpart1 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2022.CSR4.subpart2 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2022.CSR4.subpart3 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2023.CSR4.subpart1 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2023.CSR4.subpart3 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2023.CSR4.subpart4 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2024.CSR3.subpart3 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2024.CSR4.subpart1 | Green investments in enterprises | Investment in thermal renovation of buildings | 2025-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2020.CSR3.subpart4 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2020.CSR3.subpart7 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2022.CSR4.subpart1 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2022.CSR4.subpart2 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2022.CSR4.subpart3 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2023.CSR4.subpart1 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2023.CSR4.subpart3 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2023.CSR4.subpart4 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2024.CSR3.subpart3 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2024.CSR4.subpart1 | Green investments in enterprises | Investments in solar energy | 2025-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2020.CSR3.subpart4 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2020.CSR3.subpart7 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2022.CSR4.subpart1 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2022.CSR4.subpart2 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2022.CSR4.subpart3 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2023.CSR4.subpart1 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2023.CSR4.subpart3 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2023.CSR4.subpart4 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2024.CSR3.subpart3 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2024.CSR4.subpart1 | Green investments in enterprises | Investments in energy savings to support at least 800 companies under the RRP | 2025-03-31 | Completed | FALSE
2019.CSR3.subpart3 | Funding zero-emission commercial vehicles and infrastructure | Launch of the funding call | 2023-03-31 | Completed | TRUE
2020.CSR3.subpart6 | Funding zero-emission commercial vehicles and infrastructure | Launch of the funding call | 2023-03-31 | Completed | TRUE
2022.CSR4.subpart1 | Funding zero-emission commercial vehicles and infrastructure | Launch of the funding call | 2023-03-31 | Completed | TRUE
2022.CSR4.subpart2 | Funding zero-emission commercial vehicles and infrastructure | Launch of the funding call | 2023-03-31 | Completed | TRUE
2023.CSR4.subpart1 | Funding zero-emission commercial vehicles and infrastructure | Launch of the funding call | 2023-03-31 | Completed | TRUE
2023.CSR4.subpart3 | Funding zero-emission commercial vehicles and infrastructure | Launch of the funding call | 2023-03-31 | Completed | TRUE
2023.CSR4.subpart5 | Funding zero-emission commercial vehicles and infrastructure | Launch of the funding call | 2023-03-31 | Completed | TRUE
2024.CSR4.subpart1 | Funding zero-emission commercial vehicles and infrastructure | Launch of the funding call | 2023-03-31 | Completed | TRUE
2024.CSR4.subpart2 | Funding zero-emission commercial vehicles and infrastructure | Launch of the funding call | 2023-03-31 | Completed | TRUE
2019.CSR3.subpart3 | Photovoltaic systems | Installation of photovoltaic systems | 2025-12-31 | Not completed | TRUE
2020.CSR3.subpart7 | Photovoltaic systems | Installation of photovoltaic systems | 2025-12-31 | Not completed | TRUE
2022.CSR4.subpart1 | Photovoltaic systems | Installation of photovoltaic systems | 2025-12-31 | Not completed | TRUE
2022.CSR4.subpart2 | Photovoltaic systems | Installation of photovoltaic systems | 2025-12-31 | Not completed | TRUE
2023.CSR4.subpart1 | Photovoltaic systems | Installation of photovoltaic systems | 2025-12-31 | Not completed | TRUE
2023.CSR4.subpart3 | Photovoltaic systems | Installation of photovoltaic systems | 2025-12-31 | Not completed | TRUE
2024.CSR4.subpart1 | Photovoltaic systems | Installation of photovoltaic systems | 2025-12-31 | Not completed | TRUE
2019.CSR3.subpart3 | Photovoltaic systems | Installation of of photovoltaic systems | 2024-12-31 | Completed | TRUE
2020.CSR3.subpart7 | Photovoltaic systems | Installation of of photovoltaic systems | 2024-12-31 | Completed | TRUE
2022.CSR4.subpart1 | Photovoltaic systems | Installation of of photovoltaic systems | 2024-12-31 | Completed | TRUE
2022.CSR4.subpart2 | Photovoltaic systems | Installation of of photovoltaic systems | 2024-12-31 | Completed | TRUE
2023.CSR4.subpart1 | Photovoltaic systems | Installation of of photovoltaic systems | 2024-12-31 | Completed | TRUE
2023.CSR4.subpart3 | Photovoltaic systems | Installation of of photovoltaic systems | 2024-12-31 | Completed | TRUE
2024.CSR4.subpart1 | Photovoltaic systems | Installation of of photovoltaic systems | 2024-12-31 | Completed | TRUE
2019.CSR3.subpart3 | Photovoltaic systems | Publication of the guidelines | 2023-12-31 | Completed | TRUE
2020.CSR3.subpart7 | Photovoltaic systems | Publication of the guidelines | 2023-12-31 | Completed | TRUE
2022.CSR4.subpart1 | Photovoltaic systems | Publication of the guidelines | 2023-12-31 | Completed | TRUE
2022.CSR4.subpart2 | Photovoltaic systems | Publication of the guidelines | 2023-12-31 | Completed | TRUE
2023.CSR4.subpart1 | Photovoltaic systems | Publication of the guidelines | 2023-12-31 | Completed | TRUE
2023.CSR4.subpart3 | Photovoltaic systems | Publication of the guidelines | 2023-12-31 | Completed | TRUE
2024.CSR4.subpart1 | Photovoltaic systems | Publication of the guidelines | 2023-12-31 | Completed | TRUE
2019.CSR3.subpart4 | National Financial Education Strategy | Strategy document | 2021-09-28 | Fulfilled | FALSE
2020.CSR2.subpart1 | National Financial Education Strategy | Strategy document | 2021-09-28 | Fulfilled | FALSE
2023.CSR3.subpart2 | National Financial Education Strategy | Strategy document | 2021-09-28 | Fulfilled | FALSE
2023.CSR4.subpart6 | National Financial Education Strategy | Strategy document | 2021-09-28 | Fulfilled | FALSE
2024.CSR3.subpart2 | National Financial Education Strategy | Strategy document | 2021-09-28 | Fulfilled | FALSE
2019.CSR3.subpart4 | National Financial Education Strategy | Finalisation of the Competence Framework for financial education | 2023-09-30 | Completed | FALSE
2020.CSR2.subpart1 | National Financial Education Strategy | Finalisation of the Competence Framework for financial education | 2023-09-30 | Completed | FALSE
2023.CSR3.subpart2 | National Financial Education Strategy | Finalisation of the Competence Framework for financial education | 2023-09-30 | Completed | FALSE
2023.CSR4.subpart6 | National Financial Education Strategy | Finalisation of the Competence Framework for financial education | 2023-09-30 | Completed | FALSE
2024.CSR3.subpart2 | National Financial Education Strategy | Finalisation of the Competence Framework for financial education | 2023-09-30 | Completed | FALSE
2019.CSR3.subpart4 | Start-up package | Entry into force of the start-up package | 2024-01-01 | Completed | FALSE
2019.CSR3.subpart5 | Start-up package | Entry into force of the start-up package | 2024-01-01 | Completed | FALSE
2020.CSR3.subpart1 | Start-up package | Entry into force of the start-up package | 2024-01-01 | Completed | FALSE
2024.CSR3.subpart3 | Start-up package | Entry into force of the start-up package | 2024-01-01 | Completed | FALSE
2019.CSR3.subpart4 | Strengthening equity capital | Decree on the conversion of state guaranteed loans into equity | 2021-09-28 | Fulfilled | FALSE
2024.CSR3.subpart3 | Strengthening equity capital | Decree on the conversion of state guaranteed loans into equity | 2021-09-28 | Fulfilled | FALSE
2019.CSR3.subpart4 | Strengthening equity capital | Entry into force of the company form for investments in shareholding (SICAV) | 2022-03-31 | Completed | FALSE
2024.CSR3.subpart3 | Strengthening equity capital | Entry into force of the company form for investments in shareholding (SICAV) | 2022-03-31 | Completed | FALSE
2019.CSR3.subpart4 | Digitalisation of SMEs | Approval and publication of the relevant guidelines and contracts for KMU.DIGITAL 3.0 | 2021-03-31 | Fulfilled | FALSE
2024.CSR3.subpart3 | Digitalisation of SMEs | Approval and publication of the relevant guidelines and contracts for KMU.DIGITAL 3.0 | 2021-03-31 | Fulfilled | FALSE
2019.CSR3.subpart4 | Digitalisation of SMEs | Approval and publication of the relevant guidelines and contracts for KMU.E-Commerce | 2021-03-31 | Fulfilled | FALSE
2024.CSR3.subpart3 | Digitalisation of SMEs | Approval and publication of the relevant guidelines and contracts for KMU.E-Commerce | 2021-03-31 | Fulfilled | FALSE
2019.CSR3.subpart4 | Digitalisation of SMEs | Completion of SME digitalisation projects | 2023-12-31 | Completed | FALSE
2024.CSR3.subpart3 | Digitalisation of SMEs | Completion of SME digitalisation projects | 2023-12-31 | Completed | FALSE
2019.CSR3.subpart4 | Digital investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-30 | Fulfilled | FALSE
2020.CSR3.subpart4 | Digital investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-30 | Fulfilled | FALSE
2024.CSR3.subpart3 | Digital investments in enterprises | Entry into force of the amendment to the Investment Premium Act to reflect the budget increase as a result of the RRP | 2021-06-30 | Fulfilled | FALSE
2019.CSR3.subpart4 | Digital investments in enterprises | Digitalisation investments in at least 7 000 companies under the RRP | 2022-12-31 | Completed | FALSE
2020.CSR3.subpart4 | Digital investments in enterprises | Digitalisation investments in at least 7 000 companies under the RRP | 2022-12-31 | Completed | FALSE
2024.CSR3.subpart3 | Digital investments in enterprises | Digitalisation investments in at least 7 000 companies under the RRP | 2022-12-31 | Completed | FALSE
2019.CSR3.subpart5 | Liberalisation of business regulations | Entry into force of the occasional transport act | 2021-03-30 | Fulfilled | FALSE
2020.CSR3.subpart2 | Liberalisation of business regulations | Entry into force of the occasional transport act | 2021-03-30 | Fulfilled | FALSE
2022.CSR4.subpart2 | Liberalisation of business regulations | Entry into force of the occasional transport act | 2021-03-30 | Fulfilled | FALSE
2023.CSR4.subpart3 | Liberalisation of business regulations | Entry into force of the occasional transport act | 2021-03-30 | Fulfilled | FALSE
2024.CSR3.subpart3 | Liberalisation of business regulations | Entry into force of the occasional transport act | 2021-03-30 | Fulfilled | FALSE
2019.CSR3.subpart5 | Liberalisation of business regulations | Exemption of recharging points for electric motor vehicles and photovoltaic systems in commercial installations from authorisation requirements. | 2021-03-30 | Fulfilled | FALSE
2020.CSR3.subpart2 | Liberalisation of business regulations | Exemption of recharging points for electric motor vehicles and photovoltaic systems in commercial installations from authorisation requirements. | 2021-03-30 | Fulfilled | FALSE
2022.CSR4.subpart2 | Liberalisation of business regulations | Exemption of recharging points for electric motor vehicles and photovoltaic systems in commercial installations from authorisation requirements. | 2021-03-30 | Fulfilled | FALSE
2023.CSR4.subpart3 | Liberalisation of business regulations | Exemption of recharging points for electric motor vehicles and photovoltaic systems in commercial installations from authorisation requirements. | 2021-03-30 | Fulfilled | FALSE
2024.CSR3.subpart3 | Liberalisation of business regulations | Exemption of recharging points for electric motor vehicles and photovoltaic systems in commercial installations from authorisation requirements. | 2021-03-30 | Fulfilled | FALSE
2019.CSR3.subpart5 | Liberalisation of business regulations | Entry into force of the Grace Period Act | 2024-08-31 | Completed | FALSE
2020.CSR3.subpart2 | Liberalisation of business regulations | Entry into force of the Grace Period Act | 2024-08-31 | Completed | FALSE
2022.CSR4.subpart2 | Liberalisation of business regulations | Entry into force of the Grace Period Act | 2024-08-31 | Completed | FALSE
2023.CSR4.subpart3 | Liberalisation of business regulations | Entry into force of the Grace Period Act | 2024-08-31 | Completed | FALSE
2024.CSR3.subpart3 | Liberalisation of business regulations | Entry into force of the Grace Period Act | 2024-08-31 | Completed | FALSE
Extracted Date: 2025-04-08-13-07-12